## About
Worksheet adapted from Microsoft Office template by Sam Savage using the SIPmath™ Modeler Tools from ProbabilityManagement.org.
Random Number Generator from
Hubbard Decision Research
DRAFT, NOT FOR DISTRIBUTION. DO NOT USE FOR DECISION MAKING.
In Deterministic mode the model should give similar answers to the original template.
Checking SIPmath converts the model to an interactive simulation that performs 1,000 trials per keystroke.
Scroll Trials from 1 - 1,000
Choose Average or Percentile. Results appear as red lines
Choose Average or Percentile. Results appear as red lines
Enter duration details here, including Min, Max and Plan
To force precedence Actual Start should be the maximum of previous finish and planned start: =MAX(I5,C7)
Statistics and distribution of project finish

## Project Planner
Project Planner | [9 empty] | 95% | [40 empty] | 3
Check SIPMath for a 1,000 Trial Interactive Simulation |  |  |  |  | Trial 3 |  |  | Period Highlight: | 60 | Average |  |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | MIN DURATION | PLAN DURATION | MAX DURATION | ACTUAL START | ACTUAL DURATION | ACTIVITY FINISH | PERCENT COMPLETE |  | PROJECTED AVERAGE FINISH | PERIODS
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Activity 01 | 1 | 1 | 5 | 9 | 1 | 6 | 6 | 0% |  | 4
Activity 02 | 5 | 1 | 5 | 9 | 6 | 5 | 10 | 0% |  | 8
Activity 03 | 6 | 1 | 4 | 8 | 6 | 3 | 8 | 0% |  | 8
Activity 04 | 1 | 2 | 3 | 5 | 1 | 3 | 3 | 0% |  | 2
Activity 05 | 3 | 2 | 5 | 8 | 3 | 6 | 8 | 0% |  | 6
Activity 06 | 7 | 2 | 9 | 12 | 8 | 7 | 14 | 0% |  | 13
Activity 07 | 7 | 1 | 5 | 9 | 8 | 2 | 9 | 0% |  | 10
Activity 08 | 7 | 1 | 5 | 9 | 8 | 4 | 11 | 0% |  | 9
Activity 09 | 11 | 1 | 5 | 9 | 11 | 6 | 16 | 0% |  | 14
Activity 10 | 11 | 1 | 5 | 9 | 11 | 5 | 15 | 0% |  | 14
Project Complete |  |  |  |  | 16 | 1 | 16 |  |  | 16
|  |  |  | Average Completion Period | 16.04
|  |  |  | %ile | 90%
|  |  |  | % Value | 18 | [5 empty] | PERIODS 24: DRAFT
|  |  |  | Target Completion Period | 20 | [5 empty] | PERIODS 24: Not for Distribution
|  |  |  | Chance of Exceeding Target | 2%
SIPmath
Worksheet adapted from Microsoft Office template by Sam Savage using the SIPmath™ Modeler Tools from ProbabilityManagement.org.
Random Number Generator from
Hubbard Decision Research.

## Sheet1 (hidden)
Variable ID Start | 1 | TRUE | 0
| Var IDs |  |  |  | HDRs | Triangulars
Activity 01 | 1 | 0 | 5 | 9 | 0.7663 | 6.0994
Activity 02 | 2 | 0 | 5 | 9 | 0.6603 | 5.503
Activity 03 | 3 | 0 | 4 | 8 | 0.43095 | 3.7135
Activity 04 | 4 | 1 | 3 | 5 | 0.76318 | 3.6236
Activity 05 | 5 | 1 | 5 | 8 | 0.92805 | 6.7708
Activity 06 | 6 | 1 | 9 | 12 | 0.52136 | 7.7734
Activity 07 | 7 | 0 | 5 | 9 | 0.13167 | 2.4341
Activity 08 | 8 | 0 | 5 | 9 | 0.38494 | 4.162
Activity 09 | 9 | 0 | 5 | 9 | 0.78053 | 6.1892
Activity 10 | 10 | 0 | 5 | 9 | 0.7299 | 5.8817
|  | Average Completion Period | 16.04
|  | %ile | 0.9
|  | % Value | 18
|  | Target Completion Period | 20
|  | Chance of Exceeding Target | 0.02

## PMTable (hidden)
3 | Generated with the SIPmath™ Modeler Tools from ProbabilityManagement.org
| Index | Finish01 | Finish02 | Finish03 | Finish04 | Finish05 | Finish06 | Finish07 | Finish08 | Finish09 | Finish10 | FinishProject
| Values | 6 | 10 | 8 | 3 | 8 | 14 | 9 | 11 | 16 | 15 | 16
| 1 | 4 | 8 | 5 | 2 | 4 | 17 | 11 | 6 | 14 | 17 | 17
| 2 | 0 | 9 | 8 | 3 | 9 | 12 | 12 | 11 | 12 | 12 | 12
| 3 | 6 | 10 | 8 | 3 | 8 | 14 | 9 | 11 | 16 | 15 | 16
| 4 | 6 | 9 | 8 | 3 | 8 | 12 | 13 | 13 | 18 | 18 | 18
| 5 | 8 | 13 | 14 | 2 | 4 | 12 | 10 | 6 | 14 | 15 | 15
| 6 | 4 | 10 | 8 | 3 | 8 | 10 | 13 | 9 | 16 | 17 | 17
| 7 | 4 | 9 | 9 | 2 | 6 | 12 | 11 | 7 | 14 | 15 | 15
| 8 | 5 | 7 | 8 | 3 | 5 | 15 | 11 | 11 | 12 | 16 | 16
| 9 | 1 | 7 | 5 | 2 | 9 | 9 | 12 | 14 | 17 | 18 | 18
| 10 | 8 | 8 | 10 | 2 | 7 | 16 | 9 | 8 | 11 | 15 | 16
| 11 | 6 | 8 | 8 | 1 | 7 | 15 | 8 | 11 | 17 | 11 | 17
| 12 | 4 | 6 | 11 | 3 | 6 | 13 | 14 | 9 | 16 | 17 | 17
| 13 | 5 | 8 | 8 | 2 | 7 | 15 | 12 | 11 | 18 | 12 | 18
| 14 | 5 | 7 | 7 | 2 | 6 | 15 | 11 | 10 | 18 | 15 | 18
| 15 | 6 | 9 | 11 | 3 | 7 | 14 | 12 | 13 | 15 | 14 | 15
| 16 | 4 | 8 | 9 | 2 | 7 | 13 | 10 | 11 | 14 | 14 | 14
| 17 | 4 | 10 | 7 | 3 | 4 | 16 | 9 | 8 | 16 | 15 | 16
| 18 | 6 | 10 | 8 | 2 | 5 | 10 | 8 | 9 | 15 | 17 | 17
| 19 | 6 | 13 | 7 | 4 | 8 | 11 | 10 | 13 | 12 | 13 | 13
| 20 | 4 | 9 | 12 | 2 | 8 | 16 | 13 | 10 | 18 | 17 | 18
| 21 | 3 | 8 | 9 | 2 | 7 | 10 | 10 | 12 | 13 | 15 | 15
| 22 | 7 | 11 | 11 | 2 | 8 | 13 | 9 | 12 | 13 | 10 | 13
| 23 | 7 | 9 | 8 | 3 | 6 | 10 | 7 | 10 | 16 | 14 | 16
| 24 | 3 | 6 | 7 | 2 | 3 | 14 | 13 | 5 | 15 | 14 | 15
| 25 | 5 | 7 | 10 | 1 | 8 | 10 | 12 | 11 | 16 | 13 | 16
| 26 | 3 | 9 | 9 | 2 | 4 | 10 | 10 | 7 | 14 | 13 | 14
| 27 | 5 | 8 | 11 | 3 | 7 | 12 | 10 | 8 | 16 | 15 | 16
| 28 | 2 | 9 | 9 | 1 | 7 | 15 | 11 | 11 | 12 | 14 | 15
| 29 | 5 | 9 | 10 | 1 | 5 | 16 | 10 | 5 | 11 | 15 | 16
| 30 | 2 | 10 | 7 | 2 | 8 | 17 | 11 | 14 | 16 | 12 | 17
| 31 | 5 | 7 | 9 | 3 | 6 | 15 | 10 | 8 | 14 | 18 | 18
| 32 | 1 | 7 | 9 | 1 | 6 | 14 | 10 | 11 | 13 | 13 | 14
| 33 | 5 | 9 | 11 | 4 | 4 | 15 | 10 | 9 | 18 | 18 | 18
| 34 | 3 | 7 | 7 | 3 | 8 | 17 | 11 | 10 | 17 | 12 | 17
| 35 | 6 | 11 | 10 | 4 | 6 | 16 | 11 | 7 | 13 | 17 | 17
| 36 | 5 | 8 | 5 | 2 | 8 | 11 | 11 | 9 | 15 | 12 | 15
| 37 | 2 | 9 | 7 | 3 | 9 | 15 | 14 | 16 | 14 | 20 | 20
| 38 | 2 | 6 | 7 | 2 | 8 | 16 | 13 | 11 | 17 | 15 | 17
| 39 | 6 | 10 | 7 | 2 | 3 | 16 | 8 | 8 | 13 | 12 | 16
| 40 | 2 | 5 | 10 | 4 | 9 | 16 | 12 | 9 | 13 | 13 | 16
| 41 | 5 | 8 | 9 | 3 | 5 | 11 | 8 | 7 | 12 | 15 | 15
| 42 | 4 | 6 | 6 | 3 | 5 | 15 | 10 | 7 | 14 | 11 | 15
| 43 | 3 | 8 | 6 | 2 | 7 | 14 | 9 | 13 | 16 | 15 | 16
| 44 | 4 | 7 | 8 | 2 | 9 | 15 | 13 | 12 | 16 | 18 | 18
| 45 | 6 | 7 | 8 | 2 | 6 | 8 | 13 | 11 | 15 | 18 | 18
| 46 | 4 | 8 | 7 | 2 | 6 | 12 | 11 | 8 | 14 | 13 | 14
| 47 | 3 | 4 | 9 | 2 | 3 | 13 | 8 | 7 | 15 | 13 | 15
| 48 | 4 | 6 | 10 | 2 | 5 | 12 | 8 | 5 | 16 | 10 | 16
| 49 | 4 | 10 | 10 | 2 | 5 | 10 | 11 | 7 | 13 | 15 | 15
| 50 | 3 | 8 | 9 | 2 | 5 | 13 | 11 | 7 | 13 | 15 | 15
| 51 | 6 | 8 | 6 | 3 | 7 | 16 | 9 | 9 | 14 | 14 | 16
| 52 | 2 | 8 | 7 | 4 | 5 | 14 | 11 | 6 | 12 | 15 | 15
| 53 | 3 | 10 | 10 | 2 | 6 | 16 | 10 | 13 | 15 | 16 | 16
| 54 | 2 | 12 | 7 | 3 | 5 | 11 | 13 | 9 | 17 | 14 | 17
| 55 | 5 | 8 | 6 | 2 | 8 | 10 | 13 | 11 | 13 | 17 | 17
| 56 | 8 | 8 | 11 | 1 | 6 | 10 | 9 | 7 | 16 | 13 | 16
| 57 | 0 | 12 | 9 | 1 | 5 | 13 | 8 | 5 | 15 | 16 | 16
| 58 | 5 | 8 | 8 | 2 | 7 | 12 | 8 | 8 | 11 | 14 | 14
| 59 | 3 | 5 | 9 | 2 | 6 | 11 | 11 | 9 | 13 | 14 | 14
| 60 | 3 | 12 | 8 | 2 | 7 | 12 | 12 | 11 | 13 | 17 | 17
| 61 | 6 | 7 | 9 | 1 | 6 | 13 | 11 | 11 | 16 | 14 | 16
| 62 | 2 | 8 | 8 | 2 | 6 | 12 | 12 | 7 | 15 | 18 | 18
| 63 | 6 | 12 | 12 | 3 | 5 | 13 | 12 | 10 | 16 | 17 | 17
| 64 | 6 | 9 | 8 | 3 | 9 | 17 | 11 | 14 | 17 | 11 | 17
| 65 | 3 | 7 | 11 | 2 | 8 | 12 | 11 | 15 | 17 | 14 | 17
| 66 | 5 | 6 | 9 | 4 | 8 | 15 | 9 | 7 | 10 | 17 | 17
| 67 | 1 | 6 | 8 | 3 | 5 | 17 | 10 | 10 | 16 | 13 | 17
| 68 | 3 | 7 | 10 | 3 | 4 | 13 | 11 | 10 | 15 | 15 | 15
| 69 | 4 | 8 | 11 | 3 | 7 | 10 | 13 | 10 | 15 | 16 | 16
| 70 | 4 | 9 | 6 | 3 | 5 | 10 | 12 | 7 | 14 | 14 | 14
| 71 | 5 | 10 | 9 | 3 | 8 | 12 | 11 | 11 | 15 | 14 | 15
| 72 | 4 | 5 | 11 | 1 | 6 | 14 | 11 | 9 | 16 | 15 | 16
| 73 | 5 | 7 | 8 | 4 | 8 | 12 | 12 | 11 | 14 | 19 | 19
| 74 | 2 | 8 | 10 | 3 | 6 | 8 | 12 | 10 | 15 | 16 | 16
| 75 | 3 | 12 | 7 | 3 | 7 | 10 | 12 | 11 | 12 | 17 | 17
| 76 | 5 | 6 | 9 | 2 | 7 | 13 | 10 | 12 | 14 | 14 | 14
| 77 | 6 | 8 | 6 | 3 | 7 | 16 | 12 | 13 | 16 | 14 | 16
| 78 | 4 | 12 | 7 | 3 | 6 | 15 | 11 | 8 | 16 | 15 | 16
| 79 | 4 | 5 | 10 | 3 | 3 | 15 | 7 | 6 | 13 | 13 | 15
| 80 | 7 | 10 | 9 | 4 | 7 | 10 | 9 | 13 | 15 | 17 | 17
| 81 | 8 | 13 | 8 | 2 | 7 | 15 | 11 | 9 | 11 | 16 | 16
| 82 | 4 | 9 | 7 | 2 | 7 | 12 | 13 | 14 | 15 | 12 | 15
| 83 | 6 | 10 | 10 | 4 | 6 | 7 | 10 | 6 | 14 | 14 | 14
| 84 | 5 | 6 | 8 | 1 | 5 | 17 | 12 | 9 | 16 | 14 | 17
| 85 | 6 | 9 | 6 | 3 | 4 | 11 | 11 | 3 | 15 | 14 | 15
| 86 | 3 | 5 | 6 | 3 | 8 | 17 | 10 | 13 | 14 | 11 | 17
| 87 | 8 | 10 | 11 | 1 | 9 | 14 | 12 | 13 | 13 | 12 | 14
| 88 | 3 | 5 | 11 | 2 | 8 | 9 | 10 | 14 | 18 | 14 | 18
| 89 | 2 | 11 | 8 | 3 | 6 | 17 | 11 | 10 | 17 | 16 | 17
| 90 | 5 | 10 | 12 | 2 | 4 | 15 | 12 | 9 | 18 | 16 | 18
| 91 | 6 | 11 | 9 | 3 | 6 | 9 | 11 | 7 | 15 | 17 | 17
| 92 | 5 | 7 | 8 | 1 | 6 | 12 | 7 | 11 | 18 | 14 | 18
| 93 | 1 | 7 | 12 | 4 | 7 | 14 | 9 | 8 | 13 | 13 | 14
| 94 | 3 | 7 | 10 | 2 | 5 | 13 | 10 | 12 | 15 | 15 | 15
| 95 | 4 | 10 | 9 | 3 | 6 | 17 | 11 | 9 | 11 | 16 | 17
| 96 | 1 | 9 | 8 | 3 | 6 | 16 | 10 | 9 | 14 | 16 | 16
| 97 | 6 | 10 | 7 | 3 | 4 | 16 | 8 | 11 | 14 | 15 | 16
| 98 | 5 | 6 | 10 | 2 | 6 | 10 | 9 | 8 | 14 | 13 | 14
| 99 | 6 | 9 | 10 | 2 | 6 | 14 | 10 | 10 | 15 | 10 | 15
| 100 | 7 | 10 | 9 | 2 | 4 | 9 | 12 | 8 | 17 | 15 | 17
| 101 | 3 | 8 | 11 | 3 | 7 | 7 | 8 | 9 | 13 | 10 | 13
| 102 | 8 | 12 | 10 | 3 | 5 | 15 | 12 | 9 | 16 | 15 | 16
| 103 | 6 | 7 | 9 | 3 | 3 | 10 | 12 | 7 | 17 | 18 | 18
| 104 | 8 | 11 | 11 | 2 | 5 | 10 | 12 | 8 | 14 | 16 | 16
| 105 | 4 | 7 | 9 | 3 | 5 | 10 | 7 | 7 | 17 | 17 | 17
| 106 | 3 | 8 | 7 | 1 | 8 | 15 | 11 | 13 | 14 | 16 | 16
| 107 | 4 | 11 | 9 | 3 | 9 | 16 | 14 | 10 | 15 | 16 | 16
| 108 | 6 | 11 | 12 | 1 | 8 | 17 | 11 | 9 | 11 | 14 | 17
| 109 | 6 | 10 | 5 | 4 | 7 | 13 | 10 | 12 | 13 | 12 | 13
| 110 | 6 | 9 | 10 | 2 | 6 | 14 | 11 | 8 | 14 | 16 | 16
| 111 | 2 | 9 | 8 | 3 | 7 | 12 | 8 | 10 | 15 | 16 | 16
| 112 | 4 | 7 | 9 | 2 | 8 | 8 | 13 | 9 | 19 | 17 | 19
| 113 | 4 | 5 | 9 | 3 | 6 | 12 | 11 | 8 | 14 | 14 | 14
| 114 | 3 | 6 | 11 | 2 | 3 | 10 | 11 | 5 | 17 | 16 | 17
| 115 | 7 | 10 | 7 | 2 | 8 | 15 | 11 | 14 | 15 | 12 | 15
| 116 | 8 | 9 | 12 | 1 | 8 | 15 | 12 | 10 | 15 | 15 | 15
| 117 | 4 | 12 | 8 | 3 | 8 | 15 | 8 | 9 | 15 | 12 | 15
| 118 | 4 | 5 | 9 | 2 | 6 | 12 | 11 | 11 | 17 | 12 | 17
| 119 | 5 | 7 | 9 | 2 | 9 | 16 | 13 | 14 | 15 | 15 | 16
| 120 | 4 | 9 | 9 | 1 | 7 | 13 | 13 | 11 | 14 | 16 | 16
| 121 | 7 | 9 | 9 | 2 | 6 | 8 | 10 | 9 | 11 | 17 | 17
| 122 | 5 | 11 | 10 | 1 | 7 | 10 | 8 | 7 | 14 | 15 | 15
| 123 | 1 | 9 | 11 | 3 | 7 | 16 | 10 | 8 | 11 | 17 | 17
| 124 | 4 | 9 | 7 | 2 | 7 | 12 | 9 | 7 | 11 | 14 | 14
| 125 | 6 | 10 | 10 | 2 | 7 | 12 | 10 | 10 | 15 | 13 | 15
| 126 | 2 | 9 | 11 | 3 | 5 | 16 | 6 | 10 | 10 | 13 | 16
| 127 | 5 | 8 | 9 | 2 | 7 | 14 | 9 | 12 | 13 | 15 | 15
| 128 | 1 | 7 | 9 | 4 | 7 | 10 | 7 | 11 | 13 | 13 | 13
| 129 | 4 | 7 | 7 | 2 | 9 | 14 | 9 | 9 | 16 | 14 | 16
| 130 | 6 | 7 | 8 | 2 | 7 | 14 | 11 | 10 | 14 | 16 | 16
| 131 | 3 | 10 | 9 | 3 | 5 | 16 | 13 | 8 | 19 | 17 | 19
| 132 | 6 | 9 | 6 | 3 | 3 | 9 | 11 | 5 | 12 | 16 | 16
| 133 | 4 | 10 | 5 | 2 | 7 | 16 | 10 | 9 | 11 | 14 | 16
| 134 | 2 | 8 | 9 | 2 | 6 | 13 | 10 | 9 | 15 | 15 | 15
| 135 | 7 | 11 | 8 | 3 | 5 | 11 | 12 | 6 | 13 | 14 | 14
| 136 | 4 | 9 | 10 | 3 | 4 | 7 | 8 | 3 | 11 | 15 | 15
| 137 | 5 | 11 | 8 | 1 | 8 | 15 | 15 | 11 | 19 | 17 | 19
| 138 | 6 | 9 | 9 | 4 | 8 | 17 | 13 | 9 | 13 | 14 | 17
| 139 | 0 | 10 | 7 | 2 | 7 | 14 | 7 | 13 | 13 | 14 | 14
| 140 | 4 | 9 | 9 | 2 | 7 | 11 | 9 | 12 | 14 | 14 | 14
| 141 | 7 | 7 | 9 | 2 | 7 | 14 | 8 | 14 | 14 | 13 | 14
| 142 | 3 | 7 | 10 | 1 | 8 | 11 | 13 | 11 | 16 | 17 | 17
| 143 | 4 | 8 | 11 | 1 | 5 | 14 | 9 | 8 | 14 | 12 | 14
| 144 | 6 | 12 | 8 | 2 | 5 | 14 | 10 | 10 | 13 | 14 | 14
| 145 | 2 | 11 | 8 | 2 | 7 | 13 | 11 | 9 | 14 | 15 | 15
| 146 | 1 | 9 | 6 | 2 | 6 | 8 | 10 | 7 | 16 | 18 | 18
| 147 | 5 | 7 | 9 | 3 | 5 | 15 | 11 | 7 | 12 | 11 | 15
| 148 | 1 | 5 | 11 | 2 | 5 | 14 | 11 | 9 | 14 | 14 | 14
| 149 | 6 | 9 | 11 | 3 | 4 | 16 | 11 | 7 | 17 | 15 | 17
| 150 | 4 | 11 | 9 | 4 | 6 | 9 | 10 | 9 | 14 | 16 | 16
| 151 | 5 | 6 | 8 | 1 | 6 | 15 | 11 | 12 | 13 | 15 | 15
| 152 | 6 | 8 | 10 | 3 | 6 | 14 | 10 | 10 | 14 | 18 | 18
| 153 | 5 | 8 | 10 | 1 | 7 | 12 | 11 | 12 | 16 | 17 | 17
| 154 | 2 | 10 | 9 | 3 | 9 | 16 | 12 | 12 | 14 | 16 | 16
| 155 | 4 | 9 | 6 | 3 | 5 | 15 | 14 | 8 | 14 | 21 | 21
| 156 | 4 | 7 | 7 | 2 | 7 | 13 | 8 | 12 | 14 | 13 | 14
| 157 | 2 | 5 | 10 | 2 | 4 | 12 | 8 | 8 | 10 | 17 | 17
| 158 | 6 | 11 | 7 | 3 | 7 | 11 | 12 | 12 | 14 | 17 | 17
| 159 | 8 | 12 | 9 | 3 | 5 | 14 | 8 | 9 | 16 | 17 | 17
| 160 | 4 | 4 | 9 | 2 | 7 | 8 | 9 | 12 | 15 | 11 | 15
| 161 | 7 | 7 | 11 | 1 | 7 | 13 | 9 | 8 | 15 | 13 | 15
| 162 | 6 | 6 | 9 | 2 | 3 | 15 | 13 | 8 | 17 | 13 | 17
| 163 | 8 | 8 | 10 | 2 | 5 | 15 | 9 | 6 | 15 | 17 | 17
| 164 | 4 | 11 | 7 | 2 | 9 | 18 | 12 | 15 | 16 | 16 | 18
| 165 | 6 | 10 | 10 | 3 | 5 | 10 | 10 | 10 | 16 | 13 | 16
| 166 | 7 | 10 | 9 | 3 | 5 | 13 | 9 | 7 | 13 | 12 | 13
| 167 | 4 | 12 | 12 | 1 | 6 | 16 | 13 | 9 | 17 | 17 | 17
| 168 | 5 | 8 | 8 | 3 | 7 | 13 | 10 | 7 | 14 | 14 | 14
| 169 | 8 | 12 | 10 | 1 | 5 | 13 | 11 | 10 | 12 | 14 | 14
| 170 | 4 | 10 | 8 | 2 | 5 | 14 | 11 | 7 | 14 | 15 | 15
| 171 | 6 | 10 | 11 | 3 | 4 | 16 | 11 | 10 | 14 | 12 | 16
| 172 | 2 | 8 | 9 | 3 | 6 | 12 | 12 | 7 | 18 | 18 | 18
| 173 | 4 | 10 | 9 | 1 | 5 | 15 | 14 | 6 | 18 | 16 | 18
| 174 | 5 | 4 | 8 | 3 | 6 | 13 | 8 | 11 | 16 | 13 | 16
| 175 | 2 | 10 | 8 | 4 | 4 | 11 | 8 | 8 | 13 | 16 | 16
| 176 | 2 | 7 | 8 | 1 | 5 | 9 | 10 | 7 | 16 | 15 | 16
| 177 | 6 | 5 | 6 | 2 | 4 | 10 | 12 | 5 | 11 | 19 | 19
| 178 | 6 | 11 | 8 | 2 | 6 | 11 | 7 | 10 | 16 | 16 | 16
| 179 | 4 | 10 | 9 | 4 | 5 | 10 | 9 | 9 | 12 | 15 | 15
| 180 | 4 | 5 | 8 | 3 | 5 | 11 | 7 | 7 | 16 | 13 | 16
| 181 | 7 | 7 | 10 | 2 | 8 | 14 | 12 | 13 | 18 | 12 | 18
| 182 | 4 | 6 | 6 | 3 | 8 | 16 | 15 | 9 | 20 | 16 | 20
| 183 | 3 | 9 | 8 | 1 | 6 | 12 | 7 | 11 | 14 | 15 | 15
| 184 | 5 | 9 | 8 | 2 | 5 | 13 | 8 | 8 | 15 | 14 | 15
| 185 | 5 | 8 | 9 | 2 | 6 | 7 | 11 | 8 | 15 | 14 | 15
| 186 | 1 | 7 | 8 | 1 | 5 | 14 | 9 | 5 | 13 | 12 | 14
| 187 | 4 | 11 | 5 | 3 | 6 | 13 | 9 | 11 | 16 | 14 | 16
| 188 | 2 | 9 | 10 | 3 | 9 | 14 | 12 | 11 | 13 | 15 | 15
| 189 | 7 | 10 | 12 | 3 | 9 | 12 | 11 | 12 | 13 | 15 | 15
| 190 | 3 | 9 | 12 | 3 | 6 | 10 | 7 | 9 | 12 | 15 | 15
| 191 | 3 | 9 | 6 | 2 | 5 | 8 | 11 | 8 | 15 | 11 | 15
| 192 | 1 | 9 | 9 | 2 | 6 | 17 | 9 | 7 | 12 | 14 | 17
| 193 | 4 | 9 | 6 | 2 | 8 | 11 | 10 | 12 | 14 | 14 | 14
| 194 | 2 | 6 | 9 | 1 | 7 | 8 | 11 | 8 | 14 | 17 | 17
| 195 | 2 | 7 | 6 | 2 | 7 | 11 | 9 | 11 | 13 | 16 | 16
| 196 | 5 | 6 | 10 | 2 | 5 | 12 | 11 | 6 | 17 | 12 | 17
| 197 | 5 | 6 | 9 | 1 | 7 | 13 | 8 | 11 | 13 | 12 | 13
| 198 | 6 | 10 | 8 | 2 | 6 | 15 | 12 | 8 | 15 | 16 | 16
| 199 | 7 | 10 | 6 | 2 | 8 | 10 | 12 | 8 | 15 | 16 | 16
| 200 | 4 | 9 | 9 | 1 | 7 | 14 | 9 | 13 | 16 | 18 | 18
| 201 | 1 | 7 | 10 | 2 | 8 | 18 | 9 | 13 | 11 | 16 | 18
| 202 | 0 | 9 | 8 | 1 | 4 | 15 | 8 | 10 | 12 | 14 | 15
| 203 | 3 | 5 | 6 | 2 | 7 | 11 | 8 | 11 | 13 | 10 | 13
| 204 | 5 | 9 | 9 | 4 | 8 | 13 | 10 | 10 | 14 | 16 | 16
| 205 | 6 | 10 | 5 | 2 | 7 | 16 | 11 | 7 | 17 | 13 | 17
| 206 | 0 | 11 | 8 | 2 | 5 | 11 | 8 | 11 | 13 | 14 | 14
| 207 | 4 | 7 | 8 | 2 | 7 | 10 | 7 | 12 | 15 | 11 | 15
| 208 | 5 | 10 | 8 | 1 | 4 | 13 | 9 | 11 | 13 | 14 | 14
| 209 | 5 | 8 | 7 | 3 | 9 | 17 | 14 | 11 | 16 | 16 | 17
| 210 | 3 | 7 | 10 | 2 | 4 | 13 | 11 | 8 | 13 | 11 | 13
| 211 | 6 | 12 | 6 | 2 | 6 | 13 | 13 | 11 | 18 | 16 | 18
| 212 | 2 | 6 | 10 | 4 | 5 | 10 | 10 | 6 | 14 | 14 | 14
| 213 | 6 | 9 | 9 | 2 | 7 | 12 | 9 | 11 | 15 | 14 | 15
| 214 | 4 | 10 | 5 | 2 | 5 | 12 | 11 | 8 | 11 | 11 | 12
| 215 | 4 | 7 | 7 | 2 | 6 | 15 | 14 | 5 | 20 | 18 | 20
| 216 | 7 | 11 | 8 | 3 | 6 | 14 | 11 | 11 | 12 | 13 | 14
| 217 | 6 | 6 | 10 | 2 | 5 | 9 | 12 | 10 | 17 | 18 | 18
| 218 | 7 | 10 | 8 | 3 | 7 | 8 | 10 | 9 | 18 | 14 | 18
| 219 | 7 | 12 | 6 | 2 | 5 | 13 | 10 | 7 | 14 | 17 | 17
| 220 | 6 | 7 | 9 | 2 | 6 | 12 | 12 | 11 | 14 | 15 | 15
| 221 | 7 | 10 | 10 | 3 | 5 | 11 | 11 | 6 | 12 | 12 | 12
| 222 | 5 | 9 | 8 | 2 | 4 | 13 | 10 | 9 | 16 | 18 | 18
| 223 | 6 | 10 | 9 | 4 | 7 | 13 | 12 | 10 | 17 | 12 | 17
| 224 | 3 | 5 | 9 | 2 | 7 | 15 | 11 | 9 | 15 | 15 | 15
| 225 | 6 | 10 | 7 | 3 | 6 | 15 | 12 | 8 | 16 | 17 | 17
| 226 | 4 | 12 | 12 | 2 | 7 | 15 | 10 | 10 | 10 | 13 | 15
| 227 | 7 | 8 | 6 | 2 | 4 | 15 | 8 | 8 | 17 | 18 | 18
| 228 | 4 | 6 | 10 | 3 | 4 | 12 | 10 | 6 | 15 | 11 | 15
| 229 | 7 | 10 | 8 | 3 | 7 | 12 | 11 | 13 | 15 | 14 | 15
| 230 | 4 | 10 | 10 | 2 | 4 | 10 | 11 | 10 | 18 | 13 | 18
| 231 | 3 | 10 | 8 | 3 | 4 | 13 | 7 | 4 | 12 | 14 | 14
| 232 | 1 | 9 | 11 | 2 | 7 | 13 | 8 | 11 | 18 | 12 | 18
| 233 | 5 | 9 | 11 | 1 | 8 | 12 | 9 | 10 | 13 | 13 | 13
| 234 | 6 | 10 | 6 | 2 | 8 | 16 | 8 | 11 | 10 | 14 | 16
| 235 | 5 | 8 | 8 | 4 | 7 | 13 | 12 | 10 | 14 | 12 | 14
| 236 | 6 | 10 | 7 | 2 | 6 | 15 | 10 | 9 | 11 | 12 | 15
| 237 | 4 | 7 | 9 | 2 | 5 | 15 | 13 | 10 | 16 | 18 | 18
| 238 | 3 | 6 | 10 | 1 | 7 | 7 | 10 | 12 | 13 | 11 | 13
| 239 | 7 | 12 | 10 | 3 | 6 | 16 | 11 | 11 | 15 | 17 | 17
| 240 | 6 | 7 | 12 | 3 | 4 | 14 | 8 | 7 | 16 | 14 | 16
| 241 | 6 | 11 | 7 | 3 | 7 | 11 | 8 | 13 | 14 | 13 | 14
| 242 | 8 | 8 | 12 | 3 | 5 | 16 | 10 | 4 | 16 | 15 | 16
| 243 | 6 | 7 | 5 | 3 | 4 | 11 | 10 | 4 | 17 | 15 | 17
| 244 | 5 | 6 | 7 | 4 | 8 | 13 | 12 | 7 | 16 | 14 | 16
| 245 | 5 | 9 | 7 | 1 | 5 | 14 | 11 | 9 | 11 | 13 | 14
| 246 | 3 | 6 | 8 | 3 | 6 | 10 | 11 | 5 | 13 | 11 | 13
| 247 | 6 | 7 | 7 | 2 | 8 | 14 | 13 | 9 | 14 | 17 | 17
| 248 | 5 | 10 | 11 | 2 | 6 | 9 | 11 | 13 | 16 | 15 | 16
| 249 | 3 | 8 | 8 | 2 | 7 | 13 | 13 | 11 | 15 | 16 | 16
| 250 | 6 | 9 | 9 | 3 | 6 | 12 | 12 | 6 | 18 | 15 | 18
| 251 | 0 | 7 | 9 | 2 | 8 | 16 | 12 | 10 | 15 | 15 | 16
| 252 | 8 | 11 | 10 | 3 | 5 | 16 | 9 | 7 | 17 | 15 | 17
| 253 | 5 | 8 | 7 | 2 | 8 | 8 | 13 | 9 | 15 | 13 | 15
| 254 | 2 | 7 | 9 | 3 | 6 | 15 | 12 | 11 | 16 | 15 | 16
| 255 | 3 | 11 | 11 | 3 | 8 | 12 | 11 | 11 | 13 | 14 | 14
| 256 | 2 | 10 | 10 | 4 | 7 | 10 | 7 | 12 | 16 | 12 | 16
| 257 | 2 | 8 | 8 | 3 | 3 | 15 | 10 | 4 | 16 | 15 | 16
| 258 | 6 | 10 | 10 | 2 | 9 | 15 | 14 | 12 | 19 | 19 | 19
| 259 | 3 | 11 | 9 | 3 | 8 | 16 | 15 | 10 | 19 | 22 | 22
| 260 | 4 | 10 | 7 | 3 | 6 | 15 | 8 | 11 | 14 | 15 | 15
| 261 | 4 | 9 | 7 | 3 | 6 | 14 | 8 | 9 | 11 | 14 | 14
| 262 | 4 | 10 | 10 | 2 | 6 | 14 | 8 | 12 | 14 | 12 | 14
| 263 | 1 | 6 | 6 | 4 | 9 | 15 | 10 | 12 | 14 | 15 | 15
| 264 | 5 | 7 | 11 | 2 | 5 | 10 | 7 | 6 | 15 | 13 | 15
| 265 | 3 | 5 | 9 | 2 | 8 | 13 | 13 | 10 | 14 | 16 | 16
| 266 | 6 | 9 | 8 | 4 | 9 | 15 | 13 | 11 | 17 | 13 | 17
| 267 | 2 | 9 | 5 | 2 | 8 | 15 | 11 | 10 | 13 | 15 | 15
| 268 | 5 | 8 | 8 | 3 | 4 | 16 | 9 | 8 | 14 | 15 | 16
| 269 | 2 | 10 | 9 | 2 | 7 | 9 | 8 | 10 | 17 | 15 | 17
| 270 | 4 | 10 | 10 | 3 | 5 | 11 | 14 | 8 | 21 | 18 | 21
| 271 | 7 | 9 | 11 | 3 | 8 | 14 | 11 | 14 | 13 | 16 | 16
| 272 | 4 | 8 | 8 | 3 | 7 | 14 | 12 | 10 | 14 | 15 | 15
| 273 | 5 | 12 | 11 | 3 | 5 | 15 | 9 | 11 | 14 | 14 | 15
| 274 | 3 | 11 | 8 | 2 | 6 | 10 | 12 | 8 | 16 | 16 | 16
| 275 | 5 | 9 | 8 | 3 | 7 | 12 | 9 | 11 | 17 | 13 | 17
| 276 | 3 | 10 | 7 | 3 | 8 | 15 | 11 | 12 | 14 | 14 | 15
| 277 | 5 | 10 | 6 | 1 | 5 | 17 | 11 | 11 | 14 | 15 | 17
| 278 | 4 | 10 | 7 | 2 | 5 | 12 | 8 | 12 | 12 | 13 | 13
| 279 | 5 | 7 | 11 | 1 | 4 | 15 | 10 | 5 | 12 | 18 | 18
| 280 | 3 | 10 | 8 | 4 | 9 | 12 | 13 | 10 | 16 | 19 | 19
| 281 | 2 | 6 | 10 | 3 | 7 | 14 | 13 | 9 | 14 | 14 | 14
| 282 | 2 | 7 | 9 | 1 | 7 | 11 | 13 | 11 | 15 | 19 | 19
| 283 | 5 | 6 | 9 | 3 | 7 | 11 | 7 | 11 | 14 | 13 | 14
| 284 | 2 | 10 | 9 | 2 | 7 | 13 | 14 | 8 | 19 | 19 | 19
| 285 | 6 | 9 | 8 | 3 | 7 | 15 | 13 | 13 | 18 | 19 | 19
| 286 | 3 | 9 | 8 | 4 | 9 | 13 | 14 | 14 | 16 | 16 | 16
| 287 | 6 | 9 | 10 | 1 | 9 | 15 | 13 | 14 | 14 | 15 | 15
| 288 | 6 | 9 | 8 | 2 | 4 | 14 | 11 | 5 | 15 | 15 | 15
| 289 | 3 | 8 | 12 | 3 | 6 | 15 | 9 | 7 | 15 | 14 | 15
| 290 | 4 | 8 | 6 | 3 | 6 | 15 | 9 | 11 | 13 | 14 | 15
| 291 | 3 | 9 | 7 | 2 | 6 | 15 | 7 | 11 | 14 | 15 | 15
| 292 | 1 | 6 | 7 | 3 | 6 | 15 | 8 | 9 | 11 | 15 | 15
| 293 | 4 | 8 | 10 | 2 | 6 | 12 | 11 | 9 | 11 | 11 | 12
| 294 | 5 | 9 | 9 | 4 | 7 | 11 | 7 | 10 | 14 | 14 | 14
| 295 | 5 | 5 | 7 | 3 | 6 | 11 | 11 | 11 | 14 | 15 | 15
| 296 | 4 | 10 | 10 | 2 | 6 | 13 | 9 | 11 | 16 | 14 | 16
| 297 | 6 | 7 | 11 | 2 | 4 | 12 | 14 | 5 | 19 | 17 | 19
| 298 | 0 | 7 | 6 | 4 | 8 | 15 | 9 | 9 | 13 | 12 | 15
| 299 | 5 | 9 | 7 | 2 | 6 | 11 | 11 | 10 | 18 | 15 | 18
| 300 | 5 | 6 | 8 | 3 | 7 | 14 | 7 | 11 | 12 | 15 | 15
| 301 | 5 | 10 | 8 | 4 | 5 | 11 | 12 | 6 | 17 | 12 | 17
| 302 | 2 | 9 | 9 | 2 | 6 | 13 | 7 | 8 | 13 | 16 | 16
| 303 | 6 | 7 | 9 | 2 | 6 | 11 | 11 | 12 | 15 | 14 | 15
| 304 | 5 | 6 | 9 | 3 | 6 | 11 | 12 | 10 | 17 | 14 | 17
| 305 | 6 | 7 | 8 | 3 | 5 | 9 | 7 | 5 | 15 | 10 | 15
| 306 | 4 | 6 | 8 | 2 | 3 | 11 | 10 | 9 | 13 | 16 | 16
| 307 | 4 | 9 | 6 | 3 | 7 | 16 | 10 | 10 | 16 | 10 | 16
| 308 | 4 | 10 | 9 | 2 | 5 | 11 | 12 | 10 | 15 | 12 | 15
| 309 | 0 | 10 | 7 | 3 | 6 | 15 | 11 | 12 | 15 | 18 | 18
| 310 | 4 | 10 | 9 | 3 | 8 | 12 | 8 | 13 | 14 | 10 | 14
| 311 | 6 | 10 | 11 | 2 | 8 | 17 | 15 | 9 | 20 | 17 | 20
| 312 | 0 | 7 | 12 | 2 | 5 | 8 | 10 | 7 | 15 | 16 | 16
| 313 | 4 | 10 | 11 | 2 | 7 | 13 | 9 | 6 | 12 | 15 | 15
| 314 | 7 | 9 | 10 | 3 | 3 | 12 | 12 | 7 | 19 | 14 | 19
| 315 | 6 | 10 | 7 | 3 | 6 | 17 | 13 | 9 | 18 | 14 | 18
| 316 | 2 | 11 | 9 | 2 | 6 | 7 | 11 | 10 | 16 | 14 | 16
| 317 | 6 | 11 | 8 | 3 | 7 | 12 | 7 | 11 | 18 | 17 | 18
| 318 | 8 | 12 | 7 | 1 | 6 | 11 | 14 | 12 | 16 | 16 | 16
| 319 | 3 | 5 | 8 | 4 | 8 | 13 | 11 | 14 | 16 | 17 | 17
| 320 | 4 | 7 | 8 | 4 | 6 | 16 | 7 | 7 | 15 | 15 | 16
| 321 | 4 | 8 | 6 | 2 | 3 | 16 | 9 | 5 | 13 | 12 | 16
| 322 | 5 | 10 | 8 | 3 | 4 | 12 | 9 | 5 | 16 | 16 | 16
| 323 | 4 | 10 | 8 | 2 | 4 | 10 | 12 | 9 | 18 | 16 | 18
| 324 | 2 | 8 | 12 | 3 | 4 | 12 | 13 | 9 | 14 | 18 | 18
| 325 | 8 | 13 | 8 | 2 | 6 | 8 | 13 | 10 | 18 | 14 | 18
| 326 | 6 | 11 | 7 | 3 | 8 | 10 | 15 | 14 | 19 | 20 | 20
| 327 | 5 | 7 | 8 | 3 | 7 | 14 | 11 | 14 | 14 | 15 | 15
| 328 | 3 | 6 | 7 | 2 | 7 | 14 | 13 | 11 | 17 | 13 | 17
| 329 | 2 | 9 | 7 | 2 | 7 | 11 | 10 | 13 | 12 | 15 | 15
| 330 | 6 | 10 | 6 | 1 | 7 | 12 | 12 | 9 | 17 | 17 | 17
| 331 | 4 | 5 | 9 | 2 | 8 | 18 | 11 | 12 | 15 | 13 | 18
| 332 | 4 | 4 | 7 | 3 | 5 | 15 | 11 | 7 | 16 | 13 | 16
| 333 | 0 | 7 | 6 | 2 | 8 | 11 | 12 | 8 | 18 | 16 | 18
| 334 | 2 | 12 | 9 | 1 | 8 | 9 | 12 | 9 | 18 | 16 | 18
| 335 | 5 | 8 | 10 | 3 | 3 | 13 | 11 | 5 | 12 | 11 | 13
| 336 | 5 | 10 | 11 | 2 | 6 | 13 | 11 | 7 | 15 | 11 | 15
| 337 | 3 | 9 | 9 | 3 | 4 | 14 | 12 | 9 | 15 | 16 | 16
| 338 | 5 | 8 | 6 | 2 | 9 | 15 | 10 | 13 | 14 | 16 | 16
| 339 | 5 | 10 | 8 | 3 | 5 | 15 | 9 | 8 | 16 | 14 | 16
| 340 | 7 | 11 | 7 | 2 | 6 | 9 | 12 | 5 | 15 | 14 | 15
| 341 | 4 | 8 | 9 | 3 | 3 | 11 | 9 | 6 | 15 | 17 | 17
| 342 | 4 | 8 | 7 | 2 | 4 | 16 | 13 | 5 | 13 | 15 | 16
| 343 | 4 | 9 | 9 | 1 | 6 | 12 | 11 | 12 | 17 | 15 | 17
| 344 | 4 | 8 | 7 | 3 | 6 | 15 | 11 | 11 | 12 | 16 | 16
| 345 | 4 | 5 | 10 | 3 | 5 | 11 | 11 | 11 | 17 | 17 | 17
| 346 | 1 | 10 | 6 | 2 | 7 | 14 | 11 | 11 | 12 | 13 | 14
| 347 | 3 | 9 | 9 | 2 | 6 | 17 | 9 | 10 | 16 | 14 | 17
| 348 | 3 | 6 | 11 | 4 | 8 | 11 | 11 | 13 | 17 | 14 | 17
| 349 | 1 | 8 | 6 | 3 | 5 | 14 | 12 | 6 | 12 | 12 | 14
| 350 | 4 | 7 | 7 | 3 | 4 | 13 | 8 | 9 | 16 | 13 | 16
| 351 | 0 | 7 | 5 | 3 | 5 | 7 | 6 | 9 | 11 | 14 | 14
| 352 | 6 | 12 | 9 | 3 | 7 | 15 | 12 | 11 | 18 | 16 | 18
| 353 | 5 | 10 | 7 | 2 | 5 | 12 | 11 | 6 | 15 | 12 | 15
| 354 | 2 | 5 | 8 | 4 | 6 | 8 | 10 | 11 | 12 | 15 | 15
| 355 | 3 | 10 | 8 | 1 | 7 | 14 | 9 | 12 | 14 | 15 | 15
| 356 | 3 | 8 | 7 | 4 | 5 | 9 | 13 | 6 | 19 | 16 | 19
| 357 | 5 | 8 | 10 | 4 | 5 | 16 | 10 | 10 | 17 | 12 | 17
| 358 | 4 | 10 | 5 | 2 | 4 | 13 | 12 | 7 | 16 | 15 | 16
| 359 | 3 | 7 | 12 | 3 | 8 | 16 | 11 | 10 | 12 | 15 | 16
| 360 | 5 | 7 | 9 | 2 | 5 | 9 | 8 | 9 | 16 | 15 | 16
| 361 | 6 | 12 | 6 | 3 | 7 | 12 | 12 | 9 | 14 | 16 | 16
| 362 | 4 | 4 | 6 | 3 | 7 | 14 | 12 | 10 | 19 | 16 | 19
| 363 | 6 | 10 | 7 | 2 | 7 | 17 | 11 | 14 | 14 | 12 | 17
| 364 | 4 | 9 | 8 | 2 | 4 | 9 | 12 | 7 | 13 | 17 | 17
| 365 | 3 | 7 | 8 | 3 | 4 | 9 | 8 | 7 | 16 | 16 | 16
| 366 | 6 | 8 | 8 | 2 | 7 | 10 | 10 | 13 | 15 | 12 | 15
| 367 | 4 | 9 | 7 | 3 | 6 | 11 | 7 | 12 | 15 | 17 | 17
| 368 | 3 | 8 | 6 | 1 | 7 | 12 | 11 | 12 | 15 | 11 | 15
| 369 | 6 | 10 | 10 | 1 | 7 | 11 | 7 | 10 | 16 | 14 | 16
| 370 | 5 | 7 | 8 | 4 | 4 | 10 | 11 | 10 | 11 | 10 | 11
| 371 | 8 | 9 | 12 | 4 | 8 | 16 | 11 | 7 | 13 | 12 | 16
| 372 | 6 | 9 | 7 | 1 | 4 | 13 | 10 | 5 | 13 | 17 | 17
| 373 | 7 | 7 | 9 | 3 | 5 | 9 | 12 | 11 | 18 | 13 | 18
| 374 | 4 | 11 | 8 | 3 | 8 | 14 | 11 | 13 | 14 | 15 | 15
| 375 | 5 | 10 | 7 | 2 | 7 | 16 | 11 | 9 | 15 | 15 | 16
| 376 | 3 | 8 | 12 | 1 | 4 | 11 | 8 | 7 | 15 | 11 | 15
| 377 | 4 | 11 | 8 | 2 | 5 | 13 | 13 | 7 | 17 | 19 | 19
| 378 | 8 | 13 | 8 | 4 | 9 | 16 | 11 | 13 | 16 | 13 | 16
| 379 | 1 | 7 | 10 | 2 | 5 | 14 | 7 | 10 | 16 | 14 | 16
| 380 | 5 | 8 | 9 | 1 | 6 | 15 | 8 | 7 | 15 | 16 | 16
| 381 | 6 | 9 | 9 | 2 | 4 | 13 | 11 | 5 | 14 | 13 | 14
| 382 | 5 | 9 | 7 | 2 | 5 | 9 | 12 | 8 | 16 | 13 | 16
| 383 | 5 | 9 | 9 | 3 | 7 | 13 | 10 | 10 | 16 | 13 | 16
| 384 | 5 | 5 | 11 | 3 | 7 | 16 | 13 | 12 | 17 | 18 | 18
| 385 | 5 | 8 | 10 | 4 | 7 | 12 | 12 | 12 | 17 | 17 | 17
| 386 | 5 | 9 | 10 | 3 | 7 | 13 | 10 | 11 | 11 | 12 | 13
| 387 | 5 | 8 | 10 | 2 | 5 | 12 | 10 | 7 | 15 | 11 | 15
| 388 | 4 | 9 | 8 | 2 | 6 | 11 | 11 | 8 | 14 | 18 | 18
| 389 | 6 | 9 | 8 | 3 | 6 | 14 | 10 | 7 | 14 | 13 | 14
| 390 | 1 | 10 | 12 | 1 | 3 | 9 | 11 | 8 | 16 | 18 | 18
| 391 | 1 | 6 | 8 | 1 | 5 | 13 | 11 | 7 | 14 | 13 | 14
| 392 | 5 | 10 | 6 | 2 | 4 | 11 | 9 | 6 | 12 | 12 | 12
| 393 | 1 | 11 | 8 | 1 | 7 | 11 | 12 | 8 | 18 | 15 | 18
| 394 | 5 | 9 | 8 | 1 | 7 | 10 | 11 | 12 | 17 | 18 | 18
| 395 | 4 | 8 | 10 | 2 | 4 | 11 | 12 | 7 | 13 | 13 | 13
| 396 | 3 | 7 | 6 | 2 | 4 | 15 | 9 | 5 | 14 | 11 | 15
| 397 | 5 | 7 | 9 | 2 | 8 | 16 | 11 | 12 | 14 | 12 | 16
| 398 | 6 | 9 | 10 | 3 | 5 | 16 | 12 | 9 | 11 | 17 | 17
| 399 | 1 | 7 | 9 | 2 | 5 | 14 | 10 | 9 | 16 | 15 | 16
| 400 | 5 | 5 | 9 | 2 | 6 | 13 | 12 | 11 | 17 | 14 | 17
| 401 | 4 | 10 | 9 | 2 | 5 | 9 | 11 | 10 | 13 | 17 | 17
| 402 | 4 | 8 | 9 | 1 | 8 | 14 | 11 | 14 | 15 | 16 | 16
| 403 | 6 | 11 | 9 | 3 | 7 | 16 | 6 | 13 | 13 | 13 | 16
| 404 | 4 | 10 | 9 | 1 | 9 | 16 | 10 | 13 | 13 | 13 | 16
| 405 | 5 | 5 | 9 | 2 | 8 | 13 | 13 | 11 | 18 | 19 | 19
| 406 | 6 | 5 | 9 | 2 | 5 | 15 | 9 | 10 | 11 | 13 | 15
| 407 | 3 | 9 | 8 | 1 | 6 | 14 | 9 | 7 | 17 | 17 | 17
| 408 | 4 | 10 | 8 | 4 | 7 | 14 | 7 | 10 | 13 | 15 | 15
| 409 | 4 | 6 | 7 | 3 | 7 | 12 | 12 | 13 | 17 | 16 | 17
| 410 | 2 | 6 | 11 | 3 | 7 | 11 | 9 | 10 | 15 | 17 | 17
| 411 | 5 | 10 | 9 | 3 | 5 | 14 | 10 | 5 | 15 | 13 | 15
| 412 | 6 | 7 | 6 | 4 | 5 | 13 | 9 | 7 | 11 | 15 | 15
| 413 | 2 | 5 | 9 | 2 | 7 | 14 | 11 | 11 | 12 | 10 | 14
| 414 | 3 | 9 | 10 | 4 | 6 | 16 | 13 | 5 | 17 | 19 | 19
| 415 | 7 | 12 | 11 | 2 | 5 | 14 | 9 | 9 | 14 | 16 | 16
| 416 | 7 | 10 | 10 | 4 | 9 | 15 | 13 | 15 | 18 | 17 | 18
| 417 | 3 | 9 | 7 | 4 | 8 | 13 | 11 | 11 | 15 | 12 | 15
| 418 | 7 | 10 | 10 | 3 | 6 | 12 | 12 | 13 | 14 | 17 | 17
| 419 | 4 | 10 | 8 | 4 | 6 | 13 | 13 | 12 | 20 | 17 | 20
| 420 | 6 | 10 | 7 | 3 | 4 | 16 | 12 | 7 | 16 | 15 | 16
| 421 | 4 | 11 | 10 | 2 | 8 | 15 | 11 | 10 | 12 | 14 | 15
| 422 | 5 | 9 | 6 | 1 | 6 | 15 | 7 | 12 | 15 | 13 | 15
| 423 | 6 | 11 | 10 | 2 | 4 | 9 | 9 | 9 | 13 | 14 | 14
| 424 | 0 | 8 | 8 | 4 | 7 | 15 | 6 | 10 | 14 | 16 | 16
| 425 | 7 | 10 | 10 | 2 | 3 | 15 | 10 | 6 | 14 | 14 | 15
| 426 | 6 | 8 | 9 | 4 | 7 | 9 | 12 | 9 | 17 | 14 | 17
| 427 | 5 | 11 | 6 | 3 | 9 | 15 | 10 | 11 | 17 | 15 | 17
| 428 | 7 | 12 | 10 | 3 | 5 | 12 | 12 | 7 | 17 | 14 | 17
| 429 | 2 | 5 | 6 | 2 | 6 | 14 | 9 | 10 | 16 | 13 | 16
| 430 | 3 | 9 | 7 | 3 | 6 | 11 | 9 | 11 | 18 | 15 | 18
| 431 | 6 | 11 | 10 | 3 | 6 | 8 | 7 | 9 | 11 | 14 | 14
| 432 | 2 | 9 | 8 | 4 | 6 | 11 | 11 | 5 | 11 | 16 | 16
| 433 | 5 | 11 | 6 | 3 | 7 | 15 | 11 | 7 | 17 | 15 | 17
| 434 | 2 | 5 | 6 | 2 | 5 | 16 | 11 | 10 | 16 | 17 | 17
| 435 | 4 | 8 | 9 | 2 | 7 | 12 | 8 | 9 | 15 | 16 | 16
| 436 | 3 | 6 | 7 | 3 | 8 | 17 | 12 | 9 | 15 | 14 | 17
| 437 | 6 | 12 | 9 | 3 | 9 | 19 | 13 | 12 | 17 | 13 | 19
| 438 | 4 | 9 | 8 | 2 | 8 | 14 | 11 | 13 | 12 | 12 | 14
| 439 | 3 | 7 | 8 | 2 | 7 | 15 | 13 | 11 | 16 | 18 | 18
| 440 | 3 | 6 | 12 | 3 | 6 | 15 | 9 | 7 | 11 | 12 | 15
| 441 | 4 | 7 | 7 | 3 | 6 | 12 | 10 | 12 | 15 | 13 | 15
| 442 | 5 | 5 | 7 | 3 | 6 | 13 | 9 | 5 | 13 | 16 | 16
| 443 | 2 | 9 | 8 | 2 | 7 | 14 | 7 | 11 | 12 | 16 | 16
| 444 | 5 | 8 | 7 | 2 | 7 | 13 | 13 | 12 | 14 | 16 | 16
| 445 | 5 | 8 | 9 | 3 | 6 | 10 | 13 | 10 | 16 | 14 | 16
| 446 | 3 | 6 | 10 | 2 | 5 | 12 | 10 | 6 | 13 | 17 | 17
| 447 | 5 | 9 | 11 | 2 | 4 | 9 | 9 | 6 | 14 | 15 | 15
| 448 | 5 | 11 | 11 | 3 | 6 | 16 | 10 | 6 | 15 | 14 | 16
| 449 | 3 | 9 | 6 | 2 | 3 | 13 | 12 | 6 | 14 | 14 | 14
| 450 | 6 | 5 | 7 | 2 | 7 | 15 | 10 | 14 | 10 | 10 | 15
| 451 | 7 | 12 | 8 | 3 | 7 | 11 | 9 | 9 | 11 | 13 | 13
| 452 | 6 | 8 | 6 | 1 | 9 | 14 | 12 | 12 | 18 | 15 | 18
| 453 | 4 | 6 | 10 | 3 | 5 | 13 | 7 | 7 | 12 | 17 | 17
| 454 | 2 | 9 | 8 | 2 | 4 | 13 | 12 | 7 | 17 | 15 | 17
| 455 | 4 | 7 | 9 | 1 | 4 | 12 | 13 | 5 | 16 | 16 | 16
| 456 | 5 | 9 | 10 | 3 | 4 | 10 | 9 | 9 | 13 | 15 | 15
| 457 | 6 | 9 | 10 | 3 | 6 | 14 | 12 | 7 | 16 | 17 | 17
| 458 | 5 | 9 | 9 | 2 | 5 | 12 | 10 | 7 | 14 | 16 | 16
| 459 | 3 | 10 | 7 | 2 | 7 | 15 | 10 | 9 | 11 | 15 | 15
| 460 | 2 | 11 | 8 | 3 | 9 | 10 | 12 | 11 | 13 | 15 | 15
| 461 | 4 | 7 | 8 | 3 | 5 | 17 | 10 | 6 | 13 | 16 | 17
| 462 | 2 | 5 | 7 | 1 | 8 | 15 | 13 | 10 | 19 | 16 | 19
| 463 | 3 | 4 | 10 | 3 | 7 | 13 | 9 | 9 | 14 | 11 | 14
| 464 | 3 | 7 | 7 | 2 | 5 | 11 | 11 | 5 | 15 | 10 | 15
| 465 | 3 | 9 | 10 | 3 | 7 | 14 | 10 | 12 | 15 | 15 | 15
| 466 | 4 | 8 | 8 | 3 | 4 | 15 | 10 | 6 | 15 | 13 | 15
| 467 | 4 | 7 | 11 | 2 | 8 | 16 | 13 | 11 | 15 | 14 | 16
| 468 | 4 | 7 | 9 | 4 | 8 | 17 | 12 | 12 | 18 | 18 | 18
| 469 | 6 | 10 | 9 | 3 | 6 | 15 | 11 | 5 | 13 | 17 | 17
| 470 | 6 | 13 | 5 | 4 | 7 | 13 | 7 | 11 | 15 | 13 | 15
| 471 | 7 | 10 | 9 | 3 | 6 | 9 | 12 | 9 | 18 | 18 | 18
| 472 | 4 | 6 | 8 | 3 | 6 | 12 | 14 | 10 | 19 | 19 | 19
| 473 | 5 | 10 | 9 | 3 | 7 | 13 | 6 | 12 | 13 | 15 | 15
| 474 | 1 | 9 | 9 | 4 | 6 | 12 | 10 | 11 | 11 | 17 | 17
| 475 | 6 | 11 | 9 | 3 | 3 | 10 | 10 | 7 | 14 | 15 | 15
| 476 | 2 | 10 | 7 | 2 | 7 | 14 | 11 | 9 | 14 | 16 | 16
| 477 | 7 | 8 | 12 | 2 | 5 | 8 | 8 | 10 | 17 | 14 | 17
| 478 | 6 | 6 | 9 | 1 | 5 | 11 | 13 | 7 | 14 | 17 | 17
| 479 | 6 | 9 | 9 | 2 | 7 | 12 | 7 | 10 | 13 | 15 | 15
| 480 | 4 | 10 | 8 | 1 | 5 | 15 | 7 | 9 | 18 | 13 | 18
| 481 | 0 | 10 | 12 | 2 | 9 | 12 | 13 | 9 | 15 | 13 | 15
| 482 | 6 | 7 | 9 | 2 | 4 | 11 | 9 | 9 | 14 | 13 | 14
| 483 | 3 | 11 | 9 | 2 | 6 | 11 | 10 | 6 | 14 | 16 | 16
| 484 | 3 | 10 | 6 | 2 | 4 | 17 | 6 | 8 | 13 | 16 | 17
| 485 | 5 | 5 | 9 | 3 | 9 | 14 | 11 | 14 | 12 | 12 | 14
| 486 | 3 | 11 | 11 | 1 | 4 | 13 | 10 | 6 | 17 | 15 | 17
| 487 | 7 | 11 | 9 | 1 | 6 | 13 | 9 | 12 | 15 | 14 | 15
| 488 | 1 | 9 | 10 | 3 | 5 | 15 | 8 | 5 | 15 | 14 | 15
| 489 | 6 | 9 | 7 | 3 | 5 | 10 | 12 | 10 | 17 | 13 | 17
| 490 | 3 | 10 | 10 | 1 | 6 | 11 | 9 | 11 | 12 | 14 | 14
| 491 | 3 | 9 | 11 | 2 | 8 | 15 | 12 | 10 | 16 | 19 | 19
| 492 | 1 | 6 | 7 | 2 | 7 | 10 | 11 | 8 | 12 | 16 | 16
| 493 | 2 | 9 | 9 | 3 | 3 | 13 | 14 | 7 | 16 | 15 | 16
| 494 | 4 | 7 | 7 | 4 | 9 | 18 | 14 | 13 | 17 | 16 | 18
| 495 | 6 | 9 | 8 | 3 | 3 | 14 | 12 | 8 | 16 | 15 | 16
| 496 | 5 | 7 | 9 | 2 | 6 | 14 | 11 | 9 | 16 | 13 | 16
| 497 | 3 | 6 | 6 | 3 | 9 | 17 | 9 | 13 | 16 | 16 | 17
| 498 | 2 | 9 | 9 | 3 | 6 | 13 | 9 | 7 | 17 | 16 | 17
| 499 | 3 | 8 | 7 | 2 | 5 | 17 | 10 | 6 | 12 | 14 | 17
| 500 | 5 | 8 | 9 | 2 | 5 | 10 | 10 | 9 | 13 | 12 | 13
| 501 | 3 | 5 | 10 | 2 | 4 | 10 | 10 | 7 | 12 | 15 | 15
| 502 | 2 | 8 | 11 | 2 | 5 | 17 | 8 | 10 | 11 | 12 | 17
| 503 | 3 | 8 | 7 | 4 | 8 | 14 | 11 | 7 | 18 | 13 | 18
| 504 | 5 | 6 | 8 | 2 | 7 | 15 | 8 | 8 | 11 | 16 | 16
| 505 | 2 | 5 | 10 | 2 | 5 | 13 | 11 | 9 | 16 | 17 | 17
| 506 | 2 | 12 | 7 | 4 | 8 | 16 | 14 | 13 | 18 | 20 | 20
| 507 | 3 | 8 | 9 | 2 | 5 | 10 | 6 | 7 | 15 | 13 | 15
| 508 | 5 | 7 | 11 | 3 | 5 | 13 | 13 | 7 | 18 | 16 | 18
| 509 | 0 | 9 | 7 | 3 | 8 | 17 | 12 | 14 | 17 | 13 | 17
| 510 | 4 | 8 | 9 | 2 | 5 | 17 | 9 | 11 | 16 | 15 | 17
| 511 | 1 | 11 | 11 | 2 | 3 | 11 | 11 | 8 | 16 | 12 | 16
| 512 | 4 | 10 | 8 | 3 | 7 | 14 | 14 | 10 | 16 | 14 | 16
| 513 | 2 | 6 | 8 | 2 | 7 | 14 | 8 | 11 | 17 | 17 | 17
| 514 | 2 | 10 | 7 | 3 | 7 | 15 | 9 | 10 | 14 | 15 | 15
| 515 | 5 | 11 | 12 | 3 | 7 | 8 | 11 | 8 | 13 | 12 | 13
| 516 | 4 | 7 | 9 | 4 | 5 | 13 | 11 | 9 | 17 | 16 | 17
| 517 | 5 | 5 | 7 | 2 | 3 | 9 | 11 | 8 | 17 | 14 | 17
| 518 | 5 | 6 | 7 | 2 | 8 | 16 | 11 | 11 | 16 | 13 | 16
| 519 | 5 | 8 | 8 | 2 | 5 | 15 | 8 | 8 | 12 | 16 | 16
| 520 | 5 | 5 | 7 | 3 | 3 | 12 | 13 | 4 | 18 | 16 | 18
| 521 | 4 | 11 | 5 | 3 | 6 | 9 | 11 | 10 | 11 | 13 | 13
| 522 | 4 | 5 | 6 | 1 | 9 | 10 | 12 | 11 | 13 | 14 | 14
| 523 | 7 | 9 | 8 | 3 | 7 | 10 | 11 | 12 | 16 | 14 | 16
| 524 | 4 | 11 | 7 | 3 | 7 | 13 | 12 | 10 | 15 | 16 | 16
| 525 | 7 | 10 | 10 | 3 | 6 | 9 | 6 | 10 | 13 | 11 | 13
| 526 | 4 | 5 | 10 | 2 | 6 | 15 | 11 | 9 | 16 | 16 | 16
| 527 | 6 | 11 | 12 | 1 | 7 | 13 | 10 | 12 | 13 | 16 | 16
| 528 | 3 | 10 | 8 | 3 | 5 | 16 | 8 | 10 | 14 | 13 | 16
| 529 | 7 | 12 | 9 | 2 | 5 | 14 | 7 | 8 | 12 | 11 | 14
| 530 | 5 | 9 | 6 | 3 | 7 | 15 | 10 | 9 | 14 | 13 | 15
| 531 | 3 | 9 | 8 | 4 | 7 | 11 | 13 | 9 | 20 | 20 | 20
| 532 | 2 | 9 | 8 | 2 | 8 | 9 | 9 | 10 | 11 | 12 | 12
| 533 | 5 | 10 | 8 | 1 | 7 | 10 | 9 | 10 | 16 | 16 | 16
| 534 | 5 | 9 | 8 | 2 | 4 | 13 | 10 | 7 | 13 | 17 | 17
| 535 | 1 | 8 | 6 | 1 | 8 | 16 | 10 | 9 | 13 | 15 | 16
| 536 | 7 | 12 | 7 | 3 | 5 | 14 | 9 | 9 | 12 | 13 | 14
| 537 | 2 | 8 | 7 | 4 | 4 | 15 | 12 | 11 | 16 | 16 | 16
| 538 | 4 | 11 | 7 | 1 | 5 | 13 | 11 | 8 | 11 | 15 | 15
| 539 | 7 | 9 | 11 | 4 | 5 | 16 | 7 | 7 | 12 | 12 | 16
| 540 | 5 | 7 | 8 | 3 | 7 | 14 | 12 | 7 | 12 | 15 | 15
| 541 | 4 | 9 | 9 | 2 | 8 | 17 | 9 | 13 | 16 | 16 | 17
| 542 | 3 | 8 | 9 | 3 | 6 | 9 | 12 | 10 | 15 | 18 | 18
| 543 | 3 | 11 | 10 | 3 | 7 | 14 | 13 | 8 | 18 | 18 | 18
| 544 | 6 | 6 | 10 | 2 | 6 | 12 | 11 | 9 | 12 | 12 | 12
| 545 | 2 | 8 | 9 | 4 | 10 | 14 | 14 | 16 | 17 | 15 | 17
| 546 | 2 | 8 | 10 | 1 | 4 | 14 | 10 | 7 | 15 | 16 | 16
| 547 | 5 | 8 | 7 | 4 | 10 | 18 | 14 | 11 | 18 | 16 | 18
| 548 | 1 | 7 | 8 | 2 | 4 | 15 | 13 | 9 | 18 | 15 | 18
| 549 | 1 | 9 | 10 | 3 | 7 | 13 | 10 | 11 | 16 | 12 | 16
| 550 | 7 | 8 | 12 | 2 | 4 | 16 | 7 | 9 | 17 | 18 | 18
| 551 | 4 | 11 | 6 | 2 | 7 | 8 | 12 | 13 | 15 | 13 | 15
| 552 | 5 | 5 | 9 | 2 | 4 | 10 | 8 | 6 | 12 | 13 | 13
| 553 | 5 | 9 | 10 | 2 | 8 | 15 | 12 | 13 | 17 | 17 | 17
| 554 | 4 | 7 | 10 | 2 | 5 | 13 | 11 | 8 | 14 | 13 | 14
| 555 | 1 | 7 | 10 | 1 | 3 | 15 | 10 | 6 | 16 | 14 | 16
| 556 | 4 | 7 | 9 | 3 | 6 | 15 | 11 | 10 | 13 | 13 | 15
| 557 | 4 | 9 | 8 | 3 | 5 | 16 | 9 | 5 | 13 | 11 | 16
| 558 | 5 | 8 | 12 | 1 | 7 | 14 | 9 | 11 | 14 | 14 | 14
| 559 | 1 | 6 | 8 | 1 | 6 | 10 | 11 | 10 | 10 | 17 | 17
| 560 | 6 | 5 | 9 | 3 | 5 | 13 | 11 | 11 | 13 | 17 | 17
| 561 | 7 | 13 | 11 | 1 | 7 | 13 | 13 | 13 | 17 | 19 | 19
| 562 | 4 | 6 | 8 | 2 | 7 | 10 | 11 | 9 | 17 | 10 | 17
| 563 | 3 | 8 | 8 | 2 | 5 | 11 | 12 | 5 | 14 | 17 | 17
| 564 | 2 | 10 | 9 | 1 | 6 | 14 | 11 | 7 | 10 | 15 | 15
| 565 | 6 | 7 | 6 | 3 | 6 | 14 | 12 | 6 | 18 | 16 | 18
| 566 | 4 | 8 | 9 | 3 | 3 | 12 | 10 | 6 | 15 | 14 | 15
| 567 | 8 | 13 | 11 | 3 | 5 | 15 | 11 | 6 | 15 | 15 | 15
| 568 | 7 | 8 | 7 | 3 | 6 | 15 | 9 | 8 | 11 | 17 | 17
| 569 | 4 | 8 | 9 | 4 | 6 | 13 | 10 | 9 | 17 | 15 | 17
| 570 | 3 | 8 | 7 | 2 | 6 | 16 | 9 | 12 | 14 | 12 | 16
| 571 | 7 | 11 | 8 | 1 | 7 | 9 | 12 | 10 | 16 | 11 | 16
| 572 | 3 | 8 | 9 | 2 | 6 | 15 | 8 | 9 | 14 | 12 | 15
| 573 | 3 | 10 | 6 | 1 | 8 | 13 | 9 | 10 | 15 | 15 | 15
| 574 | 6 | 8 | 7 | 3 | 4 | 13 | 11 | 9 | 13 | 15 | 15
| 575 | 6 | 10 | 8 | 1 | 5 | 13 | 8 | 7 | 16 | 11 | 16
| 576 | 3 | 12 | 9 | 2 | 5 | 8 | 10 | 8 | 17 | 12 | 17
| 577 | 3 | 9 | 9 | 4 | 6 | 12 | 9 | 9 | 11 | 11 | 12
| 578 | 5 | 8 | 9 | 3 | 9 | 14 | 13 | 10 | 17 | 16 | 17
| 579 | 0 | 9 | 9 | 3 | 4 | 9 | 10 | 10 | 16 | 15 | 16
| 580 | 5 | 10 | 7 | 1 | 3 | 14 | 11 | 5 | 14 | 11 | 14
| 581 | 6 | 6 | 8 | 2 | 8 | 16 | 11 | 12 | 16 | 16 | 16
| 582 | 6 | 10 | 9 | 2 | 6 | 14 | 9 | 11 | 17 | 16 | 17
| 583 | 2 | 8 | 11 | 1 | 4 | 13 | 6 | 4 | 17 | 15 | 17
| 584 | 2 | 11 | 9 | 1 | 7 | 13 | 12 | 6 | 16 | 17 | 17
| 585 | 2 | 9 | 10 | 2 | 9 | 13 | 12 | 10 | 17 | 15 | 17
| 586 | 3 | 11 | 11 | 3 | 5 | 14 | 9 | 11 | 16 | 15 | 16
| 587 | 6 | 10 | 6 | 2 | 6 | 13 | 12 | 9 | 15 | 13 | 15
| 588 | 3 | 8 | 9 | 3 | 5 | 8 | 11 | 9 | 16 | 13 | 16
| 589 | 3 | 12 | 10 | 2 | 5 | 12 | 8 | 6 | 17 | 16 | 17
| 590 | 6 | 7 | 6 | 4 | 9 | 15 | 10 | 11 | 16 | 13 | 16
| 591 | 2 | 9 | 10 | 3 | 8 | 13 | 12 | 11 | 12 | 15 | 15
| 592 | 7 | 6 | 11 | 3 | 3 | 13 | 11 | 4 | 16 | 12 | 16
| 593 | 6 | 8 | 7 | 3 | 3 | 14 | 9 | 8 | 13 | 14 | 14
| 594 | 4 | 6 | 10 | 4 | 9 | 11 | 12 | 10 | 14 | 15 | 15
| 595 | 4 | 5 | 9 | 4 | 8 | 12 | 12 | 13 | 11 | 16 | 16
| 596 | 5 | 6 | 11 | 1 | 7 | 10 | 11 | 10 | 14 | 14 | 14
| 597 | 5 | 9 | 8 | 2 | 8 | 14 | 14 | 14 | 18 | 16 | 18
| 598 | 3 | 10 | 7 | 2 | 7 | 15 | 8 | 9 | 14 | 17 | 17
| 599 | 8 | 11 | 9 | 3 | 7 | 12 | 9 | 10 | 14 | 14 | 14
| 600 | 0 | 5 | 7 | 2 | 6 | 16 | 8 | 10 | 14 | 13 | 16
| 601 | 3 | 9 | 8 | 4 | 8 | 15 | 12 | 13 | 13 | 17 | 17
| 602 | 6 | 10 | 10 | 3 | 7 | 15 | 6 | 12 | 15 | 15 | 15
| 603 | 3 | 8 | 7 | 2 | 7 | 15 | 9 | 9 | 13 | 14 | 15
| 604 | 4 | 7 | 7 | 3 | 8 | 12 | 12 | 9 | 19 | 13 | 19
| 605 | 7 | 11 | 7 | 2 | 6 | 15 | 13 | 11 | 17 | 15 | 17
| 606 | 3 | 5 | 7 | 3 | 5 | 11 | 11 | 8 | 12 | 12 | 12
| 607 | 4 | 6 | 7 | 3 | 7 | 12 | 9 | 7 | 15 | 15 | 15
| 608 | 3 | 8 | 8 | 3 | 6 | 12 | 6 | 10 | 14 | 16 | 16
| 609 | 2 | 6 | 6 | 3 | 6 | 12 | 11 | 9 | 13 | 16 | 16
| 610 | 3 | 4 | 6 | 2 | 7 | 10 | 10 | 10 | 14 | 14 | 14
| 611 | 3 | 5 | 6 | 3 | 8 | 15 | 9 | 11 | 16 | 16 | 16
| 612 | 6 | 8 | 6 | 4 | 9 | 13 | 15 | 12 | 18 | 21 | 21
| 613 | 4 | 6 | 6 | 1 | 8 | 16 | 12 | 11 | 14 | 19 | 19
| 614 | 4 | 11 | 6 | 3 | 8 | 16 | 12 | 11 | 15 | 12 | 16
| 615 | 7 | 13 | 7 | 2 | 7 | 16 | 9 | 14 | 17 | 14 | 17
| 616 | 7 | 13 | 6 | 3 | 8 | 11 | 14 | 12 | 18 | 16 | 18
| 617 | 4 | 6 | 7 | 3 | 5 | 12 | 11 | 10 | 16 | 11 | 16
| 618 | 4 | 8 | 10 | 1 | 6 | 14 | 10 | 8 | 13 | 17 | 17
| 619 | 6 | 10 | 7 | 2 | 7 | 9 | 9 | 11 | 13 | 16 | 16
| 620 | 6 | 7 | 9 | 2 | 7 | 13 | 10 | 9 | 14 | 15 | 15
| 621 | 2 | 8 | 6 | 1 | 7 | 9 | 8 | 10 | 13 | 15 | 15
| 622 | 3 | 9 | 12 | 3 | 8 | 15 | 8 | 13 | 13 | 16 | 16
| 623 | 5 | 10 | 10 | 3 | 5 | 13 | 7 | 11 | 14 | 13 | 14
| 624 | 7 | 13 | 11 | 2 | 8 | 12 | 10 | 9 | 11 | 11 | 13
| 625 | 2 | 6 | 5 | 3 | 7 | 11 | 10 | 8 | 12 | 12 | 12
| 626 | 4 | 6 | 11 | 3 | 7 | 11 | 10 | 10 | 14 | 14 | 14
| 627 | 5 | 6 | 9 | 3 | 7 | 14 | 11 | 9 | 12 | 12 | 14
| 628 | 6 | 9 | 11 | 3 | 8 | 13 | 12 | 11 | 15 | 14 | 15
| 629 | 8 | 14 | 9 | 3 | 6 | 11 | 12 | 9 | 14 | 17 | 17
| 630 | 2 | 8 | 11 | 3 | 4 | 12 | 9 | 8 | 13 | 15 | 15
| 631 | 4 | 9 | 5 | 2 | 8 | 16 | 9 | 13 | 15 | 12 | 16
| 632 | 5 | 7 | 12 | 4 | 9 | 15 | 12 | 10 | 15 | 19 | 19
| 633 | 2 | 11 | 10 | 3 | 8 | 18 | 10 | 10 | 16 | 14 | 18
| 634 | 1 | 8 | 11 | 2 | 8 | 15 | 15 | 14 | 22 | 17 | 22
| 635 | 5 | 8 | 8 | 2 | 4 | 13 | 11 | 9 | 15 | 16 | 16
| 636 | 7 | 9 | 13 | 2 | 6 | 14 | 11 | 7 | 15 | 16 | 16
| 637 | 7 | 12 | 11 | 3 | 7 | 12 | 10 | 9 | 11 | 14 | 14
| 638 | 1 | 7 | 11 | 2 | 5 | 13 | 11 | 11 | 11 | 16 | 16
| 639 | 3 | 5 | 10 | 4 | 8 | 10 | 12 | 15 | 15 | 14 | 15
| 640 | 6 | 8 | 8 | 3 | 6 | 15 | 8 | 9 | 14 | 14 | 15
| 641 | 4 | 6 | 8 | 2 | 6 | 13 | 9 | 11 | 12 | 13 | 13
| 642 | 3 | 12 | 8 | 1 | 7 | 12 | 7 | 11 | 13 | 16 | 16
| 643 | 4 | 11 | 10 | 3 | 5 | 12 | 9 | 6 | 11 | 13 | 13
| 644 | 4 | 7 | 7 | 3 | 4 | 12 | 11 | 4 | 14 | 16 | 16
| 645 | 3 | 7 | 9 | 3 | 4 | 14 | 8 | 9 | 14 | 12 | 14
| 646 | 5 | 7 | 7 | 2 | 4 | 15 | 8 | 6 | 11 | 14 | 15
| 647 | 5 | 5 | 7 | 2 | 6 | 13 | 11 | 8 | 14 | 13 | 14
| 648 | 3 | 8 | 6 | 2 | 8 | 17 | 9 | 13 | 12 | 15 | 17
| 649 | 5 | 11 | 11 | 2 | 5 | 17 | 8 | 12 | 14 | 15 | 17
| 650 | 5 | 10 | 9 | 2 | 8 | 15 | 14 | 12 | 16 | 16 | 16
| 651 | 4 | 9 | 9 | 3 | 7 | 7 | 10 | 7 | 11 | 11 | 11
| 652 | 4 | 8 | 8 | 2 | 6 | 15 | 9 | 6 | 15 | 14 | 15
| 653 | 1 | 8 | 6 | 4 | 8 | 15 | 13 | 12 | 18 | 17 | 18
| 654 | 3 | 8 | 10 | 1 | 8 | 15 | 13 | 13 | 16 | 17 | 17
| 655 | 7 | 10 | 9 | 2 | 9 | 9 | 12 | 14 | 18 | 14 | 18
| 656 | 7 | 10 | 12 | 2 | 6 | 15 | 11 | 9 | 15 | 15 | 15
| 657 | 7 | 9 | 9 | 4 | 9 | 10 | 15 | 12 | 17 | 14 | 17
| 658 | 5 | 8 | 9 | 3 | 6 | 12 | 11 | 12 | 16 | 16 | 16
| 659 | 7 | 9 | 12 | 1 | 6 | 9 | 7 | 7 | 11 | 15 | 15
| 660 | 5 | 6 | 6 | 4 | 6 | 13 | 7 | 7 | 17 | 14 | 17
| 661 | 6 | 11 | 6 | 4 | 7 | 15 | 11 | 13 | 16 | 11 | 16
| 662 | 4 | 8 | 10 | 2 | 6 | 14 | 13 | 9 | 18 | 17 | 18
| 663 | 7 | 12 | 10 | 1 | 4 | 17 | 12 | 7 | 13 | 14 | 17
| 664 | 4 | 4 | 10 | 2 | 5 | 16 | 9 | 6 | 14 | 15 | 16
| 665 | 5 | 12 | 8 | 3 | 5 | 13 | 10 | 9 | 14 | 14 | 14
| 666 | 6 | 10 | 8 | 4 | 9 | 18 | 11 | 15 | 13 | 16 | 18
| 667 | 5 | 7 | 5 | 2 | 8 | 17 | 13 | 13 | 18 | 16 | 18
| 668 | 8 | 13 | 12 | 4 | 4 | 13 | 14 | 6 | 16 | 17 | 17
| 669 | 5 | 8 | 9 | 2 | 6 | 14 | 13 | 10 | 16 | 17 | 17
| 670 | 7 | 8 | 12 | 2 | 6 | 12 | 7 | 8 | 15 | 11 | 15
| 671 | 3 | 8 | 10 | 3 | 6 | 14 | 13 | 12 | 18 | 16 | 18
| 672 | 1 | 8 | 10 | 4 | 10 | 17 | 13 | 15 | 16 | 16 | 17
| 673 | 5 | 6 | 7 | 2 | 9 | 11 | 14 | 15 | 17 | 18 | 18
| 674 | 1 | 8 | 7 | 3 | 7 | 10 | 11 | 13 | 15 | 13 | 15
| 675 | 1 | 9 | 6 | 3 | 5 | 15 | 6 | 9 | 10 | 13 | 15
| 676 | 4 | 8 | 9 | 4 | 4 | 9 | 8 | 6 | 12 | 16 | 16
| 677 | 5 | 10 | 8 | 2 | 6 | 16 | 6 | 9 | 14 | 17 | 17
| 678 | 4 | 8 | 8 | 4 | 6 | 13 | 11 | 11 | 17 | 14 | 17
| 679 | 5 | 6 | 11 | 3 | 7 | 13 | 11 | 10 | 17 | 15 | 17
| 680 | 5 | 10 | 8 | 3 | 6 | 11 | 10 | 8 | 14 | 15 | 15
| 681 | 1 | 8 | 7 | 1 | 7 | 9 | 12 | 10 | 15 | 13 | 15
| 682 | 7 | 10 | 9 | 2 | 3 | 14 | 12 | 3 | 16 | 18 | 18
| 683 | 4 | 10 | 8 | 4 | 8 | 16 | 10 | 14 | 13 | 11 | 16
| 684 | 3 | 4 | 10 | 4 | 10 | 17 | 13 | 11 | 14 | 17 | 17
| 685 | 0 | 12 | 8 | 2 | 7 | 9 | 11 | 11 | 11 | 15 | 15
| 686 | 5 | 9 | 10 | 4 | 9 | 16 | 15 | 14 | 18 | 15 | 18
| 687 | 6 | 11 | 11 | 2 | 7 | 17 | 9 | 7 | 12 | 17 | 17
| 688 | 4 | 5 | 8 | 2 | 6 | 17 | 13 | 9 | 15 | 18 | 18
| 689 | 7 | 8 | 8 | 3 | 7 | 14 | 11 | 6 | 17 | 13 | 17
| 690 | 7 | 12 | 9 | 2 | 7 | 15 | 11 | 10 | 11 | 12 | 15
| 691 | 5 | 7 | 7 | 2 | 8 | 13 | 14 | 8 | 15 | 18 | 18
| 692 | 3 | 10 | 8 | 4 | 8 | 15 | 11 | 13 | 14 | 16 | 16
| 693 | 4 | 9 | 9 | 3 | 8 | 10 | 7 | 13 | 12 | 12 | 13
| 694 | 4 | 5 | 8 | 3 | 7 | 11 | 12 | 7 | 14 | 11 | 14
| 695 | 3 | 5 | 9 | 2 | 4 | 16 | 7 | 8 | 16 | 15 | 16
| 696 | 4 | 7 | 7 | 2 | 6 | 8 | 9 | 9 | 15 | 15 | 15
| 697 | 6 | 10 | 11 | 2 | 5 | 15 | 8 | 10 | 11 | 11 | 15
| 698 | 4 | 7 | 6 | 3 | 6 | 16 | 13 | 11 | 16 | 15 | 16
| 699 | 4 | 8 | 9 | 3 | 3 | 16 | 12 | 5 | 14 | 14 | 16
| 700 | 5 | 5 | 7 | 3 | 8 | 10 | 13 | 14 | 17 | 16 | 17
| 701 | 0 | 9 | 7 | 2 | 5 | 11 | 9 | 5 | 14 | 14 | 14
| 702 | 5 | 8 | 7 | 4 | 8 | 13 | 14 | 11 | 15 | 19 | 19
| 703 | 4 | 8 | 9 | 4 | 8 | 15 | 12 | 13 | 16 | 17 | 17
| 704 | 4 | 10 | 11 | 3 | 4 | 8 | 11 | 6 | 16 | 14 | 16
| 705 | 5 | 6 | 9 | 2 | 6 | 13 | 11 | 12 | 14 | 14 | 14
| 706 | 4 | 9 | 8 | 3 | 6 | 17 | 13 | 8 | 18 | 16 | 18
| 707 | 6 | 7 | 7 | 2 | 7 | 13 | 9 | 8 | 14 | 16 | 16
| 708 | 3 | 10 | 6 | 2 | 5 | 11 | 9 | 9 | 14 | 13 | 14
| 709 | 2 | 9 | 7 | 3 | 6 | 17 | 10 | 8 | 16 | 16 | 17
| 710 | 7 | 10 | 9 | 1 | 6 | 14 | 12 | 9 | 18 | 18 | 18
| 711 | 6 | 8 | 9 | 2 | 6 | 15 | 10 | 7 | 11 | 18 | 18
| 712 | 3 | 5 | 11 | 2 | 4 | 15 | 8 | 7 | 11 | 10 | 15
| 713 | 2 | 10 | 7 | 4 | 10 | 17 | 11 | 14 | 17 | 13 | 17
| 714 | 3 | 8 | 9 | 3 | 4 | 13 | 10 | 5 | 13 | 17 | 17
| 715 | 7 | 7 | 9 | 4 | 8 | 12 | 13 | 10 | 14 | 17 | 17
| 716 | 5 | 8 | 9 | 3 | 5 | 14 | 11 | 6 | 15 | 13 | 15
| 717 | 3 | 11 | 10 | 2 | 9 | 16 | 16 | 14 | 20 | 21 | 21
| 718 | 5 | 6 | 11 | 2 | 5 | 15 | 12 | 11 | 14 | 15 | 15
| 719 | 4 | 6 | 6 | 3 | 4 | 15 | 14 | 7 | 18 | 15 | 18
| 720 | 5 | 5 | 7 | 3 | 6 | 15 | 10 | 8 | 13 | 18 | 18
| 721 | 4 | 10 | 5 | 1 | 5 | 15 | 8 | 10 | 17 | 11 | 17
| 722 | 4 | 7 | 10 | 4 | 8 | 15 | 10 | 8 | 12 | 18 | 18
| 723 | 3 | 8 | 9 | 3 | 8 | 15 | 10 | 10 | 12 | 12 | 15
| 724 | 2 | 8 | 11 | 3 | 8 | 15 | 11 | 11 | 10 | 15 | 15
| 725 | 7 | 9 | 8 | 1 | 9 | 15 | 10 | 11 | 12 | 13 | 15
| 726 | 6 | 10 | 9 | 4 | 8 | 14 | 8 | 10 | 14 | 14 | 14
| 727 | 5 | 9 | 8 | 2 | 4 | 12 | 9 | 5 | 16 | 16 | 16
| 728 | 2 | 7 | 10 | 2 | 5 | 13 | 10 | 11 | 13 | 15 | 15
| 729 | 3 | 8 | 12 | 1 | 4 | 15 | 7 | 8 | 12 | 17 | 17
| 730 | 3 | 8 | 8 | 2 | 7 | 14 | 10 | 10 | 12 | 15 | 15
| 731 | 1 | 10 | 11 | 2 | 8 | 16 | 11 | 10 | 13 | 16 | 16
| 732 | 3 | 9 | 6 | 2 | 8 | 9 | 13 | 9 | 16 | 16 | 16
| 733 | 7 | 9 | 13 | 2 | 7 | 12 | 12 | 11 | 17 | 16 | 17
| 734 | 2 | 9 | 12 | 3 | 9 | 18 | 13 | 14 | 15 | 16 | 18
| 735 | 1 | 12 | 7 | 3 | 4 | 13 | 6 | 8 | 15 | 15 | 15
| 736 | 3 | 11 | 11 | 1 | 8 | 14 | 10 | 9 | 17 | 15 | 17
| 737 | 2 | 11 | 8 | 2 | 6 | 16 | 9 | 10 | 14 | 15 | 16
| 738 | 3 | 9 | 10 | 3 | 6 | 14 | 12 | 9 | 14 | 14 | 14
| 739 | 5 | 5 | 8 | 3 | 7 | 12 | 10 | 8 | 13 | 14 | 14
| 740 | 8 | 11 | 10 | 1 | 8 | 16 | 12 | 12 | 16 | 15 | 16
| 741 | 4 | 8 | 9 | 3 | 8 | 14 | 13 | 10 | 14 | 14 | 14
| 742 | 6 | 8 | 6 | 3 | 7 | 10 | 11 | 8 | 11 | 13 | 13
| 743 | 7 | 11 | 10 | 2 | 7 | 15 | 10 | 13 | 13 | 17 | 17
| 744 | 4 | 9 | 9 | 1 | 8 | 15 | 8 | 12 | 16 | 14 | 16
| 745 | 2 | 9 | 9 | 2 | 4 | 9 | 10 | 7 | 15 | 15 | 15
| 746 | 6 | 11 | 10 | 4 | 6 | 15 | 11 | 7 | 14 | 12 | 15
| 747 | 4 | 9 | 6 | 3 | 4 | 13 | 11 | 9 | 15 | 15 | 15
| 748 | 5 | 7 | 8 | 1 | 4 | 11 | 12 | 8 | 14 | 11 | 14
| 749 | 5 | 6 | 8 | 3 | 6 | 8 | 10 | 9 | 13 | 16 | 16
| 750 | 4 | 10 | 7 | 3 | 7 | 15 | 12 | 12 | 18 | 15 | 18
| 751 | 7 | 12 | 12 | 3 | 8 | 16 | 14 | 9 | 18 | 17 | 18
| 752 | 2 | 8 | 9 | 2 | 6 | 10 | 8 | 10 | 15 | 15 | 15
| 753 | 0 | 10 | 9 | 4 | 5 | 14 | 7 | 5 | 12 | 17 | 17
| 754 | 4 | 12 | 8 | 2 | 6 | 11 | 11 | 7 | 13 | 15 | 15
| 755 | 1 | 5 | 6 | 2 | 5 | 15 | 8 | 8 | 14 | 13 | 15
| 756 | 6 | 12 | 11 | 1 | 4 | 14 | 9 | 9 | 12 | 15 | 15
| 757 | 2 | 8 | 9 | 2 | 7 | 16 | 8 | 9 | 15 | 16 | 16
| 758 | 4 | 9 | 8 | 4 | 8 | 13 | 13 | 7 | 16 | 19 | 19
| 759 | 7 | 11 | 13 | 4 | 9 | 17 | 13 | 15 | 16 | 18 | 18
| 760 | 6 | 9 | 9 | 3 | 6 | 15 | 10 | 5 | 13 | 15 | 15
| 761 | 5 | 11 | 6 | 3 | 5 | 10 | 12 | 7 | 12 | 14 | 14
| 762 | 5 | 12 | 8 | 3 | 4 | 11 | 7 | 6 | 15 | 18 | 18
| 763 | 5 | 9 | 6 | 3 | 6 | 16 | 8 | 9 | 13 | 16 | 16
| 764 | 5 | 10 | 7 | 1 | 5 | 17 | 13 | 6 | 19 | 14 | 19
| 765 | 5 | 9 | 11 | 3 | 8 | 14 | 11 | 14 | 14 | 17 | 17
| 766 | 5 | 5 | 10 | 3 | 4 | 13 | 10 | 7 | 12 | 16 | 16
| 767 | 5 | 11 | 6 | 2 | 6 | 7 | 10 | 8 | 15 | 13 | 15
| 768 | 5 | 7 | 8 | 2 | 4 | 14 | 8 | 8 | 14 | 13 | 14
| 769 | 4 | 6 | 12 | 3 | 4 | 13 | 12 | 5 | 12 | 16 | 16
| 770 | 5 | 9 | 8 | 2 | 5 | 14 | 9 | 8 | 12 | 13 | 14
| 771 | 2 | 8 | 7 | 4 | 7 | 13 | 11 | 9 | 16 | 13 | 16
| 772 | 2 | 9 | 7 | 4 | 6 | 14 | 7 | 12 | 14 | 16 | 16
| 773 | 5 | 7 | 11 | 3 | 5 | 12 | 10 | 12 | 13 | 12 | 13
| 774 | 5 | 8 | 9 | 2 | 5 | 13 | 7 | 11 | 12 | 18 | 18
| 775 | 3 | 10 | 6 | 4 | 8 | 12 | 12 | 10 | 18 | 14 | 18
| 776 | 3 | 5 | 10 | 2 | 6 | 12 | 9 | 10 | 15 | 18 | 18
| 777 | 5 | 10 | 10 | 3 | 4 | 8 | 7 | 7 | 16 | 13 | 16
| 778 | 4 | 8 | 8 | 1 | 9 | 13 | 9 | 11 | 11 | 18 | 18
| 779 | 3 | 10 | 6 | 2 | 9 | 16 | 15 | 12 | 17 | 18 | 18
| 780 | 4 | 5 | 11 | 2 | 4 | 13 | 12 | 8 | 15 | 14 | 15
| 781 | 2 | 9 | 9 | 2 | 5 | 15 | 9 | 8 | 13 | 14 | 15
| 782 | 4 | 6 | 9 | 1 | 6 | 14 | 12 | 8 | 13 | 18 | 18
| 783 | 0 | 7 | 6 | 3 | 9 | 18 | 14 | 13 | 14 | 20 | 20
| 784 | 5 | 7 | 8 | 2 | 6 | 15 | 12 | 7 | 12 | 14 | 15
| 785 | 4 | 8 | 9 | 3 | 4 | 14 | 11 | 5 | 12 | 11 | 14
| 786 | 3 | 8 | 7 | 3 | 8 | 10 | 10 | 13 | 14 | 16 | 16
| 787 | 5 | 9 | 7 | 3 | 7 | 10 | 12 | 7 | 17 | 12 | 17
| 788 | 0 | 8 | 9 | 3 | 7 | 15 | 6 | 10 | 17 | 15 | 17
| 789 | 7 | 9 | 11 | 2 | 7 | 14 | 9 | 10 | 13 | 17 | 17
| 790 | 4 | 6 | 7 | 3 | 8 | 8 | 9 | 9 | 16 | 16 | 16
| 791 | 6 | 9 | 12 | 3 | 4 | 15 | 9 | 7 | 13 | 13 | 15
| 792 | 4 | 7 | 9 | 3 | 6 | 15 | 10 | 13 | 13 | 13 | 15
| 793 | 3 | 11 | 8 | 1 | 9 | 15 | 14 | 11 | 15 | 17 | 17
| 794 | 2 | 8 | 7 | 2 | 5 | 12 | 13 | 7 | 19 | 14 | 19
| 795 | 4 | 8 | 6 | 1 | 6 | 14 | 14 | 12 | 19 | 20 | 20
| 796 | 5 | 11 | 8 | 3 | 7 | 13 | 14 | 10 | 19 | 17 | 19
| 797 | 8 | 9 | 12 | 3 | 5 | 13 | 9 | 9 | 12 | 17 | 17
| 798 | 5 | 8 | 9 | 2 | 4 | 11 | 12 | 8 | 16 | 16 | 16
| 799 | 4 | 9 | 9 | 4 | 7 | 11 | 14 | 10 | 16 | 13 | 16
| 800 | 5 | 6 | 7 | 1 | 7 | 16 | 10 | 8 | 13 | 13 | 16
| 801 | 1 | 4 | 12 | 3 | 6 | 14 | 8 | 10 | 16 | 11 | 16
| 802 | 5 | 9 | 6 | 2 | 6 | 12 | 8 | 11 | 15 | 14 | 15
| 803 | 1 | 4 | 8 | 1 | 7 | 15 | 12 | 13 | 11 | 15 | 15
| 804 | 4 | 8 | 12 | 2 | 5 | 13 | 13 | 6 | 17 | 13 | 17
| 805 | 6 | 11 | 10 | 2 | 6 | 9 | 9 | 8 | 16 | 11 | 16
| 806 | 3 | 6 | 9 | 3 | 8 | 14 | 15 | 8 | 18 | 16 | 18
| 807 | 4 | 7 | 10 | 4 | 8 | 11 | 8 | 13 | 15 | 14 | 15
| 808 | 2 | 7 | 7 | 4 | 7 | 13 | 10 | 9 | 17 | 14 | 17
| 809 | 6 | 6 | 9 | 4 | 4 | 8 | 8 | 8 | 14 | 15 | 15
| 810 | 3 | 11 | 7 | 2 | 7 | 13 | 9 | 7 | 14 | 12 | 14
| 811 | 3 | 8 | 5 | 4 | 5 | 15 | 11 | 7 | 15 | 16 | 16
| 812 | 1 | 9 | 11 | 2 | 8 | 13 | 12 | 13 | 13 | 17 | 17
| 813 | 3 | 9 | 7 | 2 | 4 | 15 | 12 | 6 | 17 | 18 | 18
| 814 | 6 | 9 | 6 | 2 | 8 | 17 | 11 | 13 | 16 | 17 | 17
| 815 | 6 | 11 | 12 | 3 | 8 | 9 | 12 | 10 | 12 | 16 | 16
| 816 | 3 | 11 | 11 | 1 | 7 | 16 | 11 | 8 | 14 | 14 | 16
| 817 | 3 | 9 | 11 | 2 | 3 | 14 | 7 | 3 | 13 | 14 | 14
| 818 | 4 | 4 | 6 | 2 | 6 | 12 | 13 | 9 | 16 | 18 | 18
| 819 | 5 | 12 | 11 | 3 | 7 | 9 | 9 | 12 | 18 | 15 | 18
| 820 | 5 | 9 | 10 | 2 | 6 | 15 | 8 | 8 | 18 | 15 | 18
| 821 | 4 | 9 | 9 | 3 | 5 | 13 | 10 | 10 | 12 | 16 | 16
| 822 | 3 | 8 | 8 | 4 | 9 | 18 | 10 | 14 | 17 | 13 | 18
| 823 | 7 | 12 | 6 | 2 | 8 | 13 | 7 | 8 | 17 | 11 | 17
| 824 | 5 | 8 | 9 | 3 | 5 | 14 | 9 | 10 | 14 | 17 | 17
| 825 | 2 | 7 | 7 | 3 | 8 | 15 | 10 | 12 | 16 | 16 | 16
| 826 | 4 | 10 | 8 | 2 | 6 | 15 | 11 | 7 | 17 | 12 | 17
| 827 | 3 | 10 | 7 | 4 | 6 | 14 | 9 | 11 | 14 | 16 | 16
| 828 | 2 | 8 | 11 | 2 | 5 | 13 | 9 | 5 | 14 | 16 | 16
| 829 | 6 | 8 | 9 | 2 | 6 | 15 | 11 | 9 | 13 | 13 | 15
| 830 | 5 | 12 | 5 | 3 | 5 | 12 | 9 | 9 | 16 | 13 | 16
| 831 | 5 | 8 | 7 | 3 | 5 | 15 | 10 | 5 | 13 | 15 | 15
| 832 | 2 | 8 | 9 | 2 | 6 | 11 | 12 | 7 | 19 | 16 | 19
| 833 | 4 | 8 | 7 | 1 | 5 | 15 | 12 | 8 | 16 | 12 | 16
| 834 | 2 | 10 | 8 | 2 | 4 | 15 | 9 | 4 | 12 | 11 | 15
| 835 | 6 | 9 | 6 | 3 | 6 | 16 | 11 | 11 | 14 | 13 | 16
| 836 | 7 | 11 | 10 | 3 | 8 | 11 | 7 | 11 | 16 | 16 | 16
| 837 | 5 | 9 | 6 | 3 | 8 | 13 | 10 | 11 | 12 | 12 | 13
| 838 | 5 | 5 | 11 | 3 | 4 | 13 | 10 | 5 | 13 | 11 | 13
| 839 | 5 | 5 | 7 | 2 | 8 | 14 | 11 | 10 | 14 | 15 | 15
| 840 | 3 | 9 | 9 | 4 | 6 | 12 | 10 | 10 | 15 | 17 | 17
| 841 | 7 | 10 | 8 | 2 | 5 | 8 | 11 | 8 | 16 | 12 | 16
| 842 | 6 | 9 | 8 | 2 | 5 | 14 | 11 | 9 | 12 | 14 | 14
| 843 | 0 | 10 | 9 | 4 | 9 | 15 | 14 | 10 | 17 | 17 | 17
| 844 | 2 | 10 | 7 | 2 | 3 | 14 | 11 | 7 | 16 | 13 | 16
| 845 | 7 | 6 | 13 | 2 | 7 | 10 | 10 | 10 | 13 | 15 | 15
| 846 | 3 | 5 | 6 | 2 | 7 | 12 | 12 | 12 | 17 | 16 | 17
| 847 | 3 | 10 | 8 | 3 | 4 | 13 | 11 | 7 | 15 | 15 | 15
| 848 | 2 | 6 | 10 | 1 | 8 | 15 | 11 | 13 | 14 | 14 | 15
| 849 | 5 | 5 | 8 | 4 | 5 | 14 | 7 | 8 | 15 | 15 | 15
| 850 | 8 | 14 | 13 | 2 | 7 | 14 | 13 | 11 | 17 | 17 | 17
| 851 | 8 | 11 | 9 | 3 | 5 | 12 | 11 | 8 | 15 | 12 | 15
| 852 | 5 | 10 | 8 | 2 | 7 | 13 | 8 | 11 | 16 | 14 | 16
| 853 | 1 | 9 | 9 | 2 | 3 | 17 | 11 | 6 | 14 | 14 | 17
| 854 | 4 | 5 | 9 | 2 | 9 | 10 | 12 | 14 | 16 | 13 | 16
| 855 | 3 | 11 | 12 | 4 | 7 | 13 | 8 | 12 | 13 | 16 | 16
| 856 | 4 | 9 | 7 | 3 | 7 | 13 | 12 | 9 | 13 | 18 | 18
| 857 | 5 | 10 | 9 | 2 | 8 | 16 | 10 | 11 | 14 | 13 | 16
| 858 | 2 | 8 | 11 | 2 | 4 | 14 | 12 | 5 | 15 | 12 | 15
| 859 | 7 | 10 | 8 | 2 | 7 | 10 | 9 | 10 | 16 | 13 | 16
| 860 | 6 | 12 | 9 | 2 | 8 | 17 | 12 | 10 | 12 | 16 | 17
| 861 | 6 | 8 | 9 | 3 | 4 | 17 | 13 | 7 | 18 | 14 | 18
| 862 | 6 | 10 | 8 | 2 | 5 | 12 | 9 | 7 | 11 | 11 | 12
| 863 | 5 | 9 | 8 | 2 | 9 | 14 | 13 | 14 | 16 | 16 | 16
| 864 | 2 | 10 | 9 | 2 | 8 | 16 | 13 | 13 | 14 | 18 | 18
| 865 | 2 | 8 | 12 | 4 | 7 | 14 | 8 | 9 | 16 | 15 | 16
| 866 | 7 | 9 | 11 | 3 | 3 | 15 | 10 | 7 | 11 | 12 | 15
| 867 | 4 | 8 | 10 | 3 | 6 | 12 | 12 | 10 | 14 | 18 | 18
| 868 | 3 | 5 | 10 | 3 | 7 | 11 | 8 | 7 | 11 | 17 | 17
| 869 | 4 | 10 | 6 | 2 | 8 | 14 | 11 | 9 | 16 | 15 | 16
| 870 | 4 | 10 | 9 | 2 | 3 | 9 | 13 | 10 | 14 | 20 | 20
| 871 | 3 | 6 | 7 | 4 | 9 | 11 | 12 | 14 | 16 | 16 | 16
| 872 | 5 | 9 | 11 | 3 | 7 | 11 | 10 | 13 | 15 | 15 | 15
| 873 | 5 | 7 | 10 | 3 | 6 | 12 | 11 | 13 | 13 | 11 | 13
| 874 | 7 | 12 | 7 | 4 | 9 | 17 | 15 | 11 | 20 | 21 | 21
| 875 | 6 | 11 | 5 | 1 | 9 | 16 | 11 | 12 | 13 | 12 | 16
| 876 | 2 | 6 | 7 | 1 | 8 | 15 | 11 | 8 | 13 | 14 | 15
| 877 | 6 | 5 | 10 | 3 | 6 | 15 | 11 | 10 | 10 | 14 | 15
| 878 | 5 | 8 | 11 | 1 | 5 | 13 | 13 | 9 | 12 | 19 | 19
| 879 | 5 | 5 | 6 | 3 | 7 | 14 | 11 | 11 | 15 | 17 | 17
| 880 | 3 | 8 | 7 | 3 | 8 | 9 | 13 | 13 | 15 | 13 | 15
| 881 | 4 | 7 | 10 | 1 | 7 | 16 | 7 | 9 | 14 | 14 | 16
| 882 | 1 | 9 | 10 | 2 | 6 | 11 | 10 | 13 | 12 | 13 | 13
| 883 | 5 | 7 | 9 | 4 | 8 | 15 | 12 | 14 | 15 | 16 | 16
| 884 | 6 | 9 | 9 | 4 | 9 | 14 | 10 | 15 | 15 | 15 | 15
| 885 | 5 | 12 | 10 | 4 | 8 | 14 | 9 | 12 | 15 | 13 | 15
| 886 | 2 | 4 | 8 | 4 | 6 | 9 | 11 | 8 | 15 | 13 | 15
| 887 | 2 | 7 | 11 | 1 | 6 | 9 | 11 | 11 | 14 | 15 | 15
| 888 | 6 | 9 | 11 | 2 | 6 | 11 | 9 | 9 | 12 | 15 | 15
| 889 | 4 | 6 | 6 | 2 | 4 | 14 | 9 | 4 | 16 | 13 | 16
| 890 | 5 | 7 | 7 | 3 | 6 | 14 | 7 | 9 | 14 | 15 | 15
| 891 | 5 | 9 | 10 | 3 | 7 | 13 | 8 | 7 | 18 | 16 | 18
| 892 | 4 | 7 | 8 | 2 | 4 | 16 | 14 | 8 | 17 | 18 | 18
| 893 | 8 | 12 | 8 | 1 | 5 | 13 | 8 | 9 | 15 | 12 | 15
| 894 | 1 | 9 | 7 | 3 | 4 | 13 | 9 | 9 | 16 | 10 | 16
| 895 | 4 | 10 | 9 | 3 | 7 | 15 | 11 | 10 | 15 | 13 | 15
| 896 | 3 | 11 | 7 | 2 | 9 | 13 | 14 | 12 | 18 | 17 | 18
| 897 | 7 | 9 | 10 | 1 | 8 | 11 | 11 | 12 | 14 | 12 | 14
| 898 | 5 | 5 | 8 | 3 | 5 | 12 | 11 | 12 | 12 | 13 | 13
| 899 | 5 | 8 | 9 | 3 | 5 | 15 | 9 | 9 | 16 | 11 | 16
| 900 | 7 | 8 | 8 | 3 | 7 | 14 | 9 | 10 | 11 | 18 | 18
| 901 | 4 | 8 | 12 | 2 | 8 | 15 | 10 | 12 | 12 | 18 | 18
| 902 | 7 | 13 | 7 | 3 | 7 | 12 | 11 | 8 | 13 | 17 | 17
| 903 | 2 | 10 | 12 | 3 | 8 | 15 | 11 | 8 | 15 | 12 | 15
| 904 | 4 | 8 | 11 | 1 | 7 | 13 | 11 | 10 | 12 | 12 | 13
| 905 | 0 | 9 | 7 | 2 | 4 | 14 | 12 | 6 | 18 | 17 | 18
| 906 | 2 | 11 | 9 | 2 | 9 | 18 | 12 | 11 | 18 | 12 | 18
| 907 | 7 | 11 | 9 | 4 | 7 | 15 | 12 | 10 | 16 | 13 | 16
| 908 | 5 | 11 | 8 | 3 | 7 | 13 | 10 | 7 | 13 | 15 | 15
| 909 | 2 | 10 | 8 | 2 | 5 | 16 | 12 | 6 | 13 | 14 | 16
| 910 | 1 | 7 | 9 | 2 | 7 | 10 | 11 | 13 | 12 | 13 | 13
| 911 | 1 | 7 | 10 | 2 | 5 | 12 | 6 | 12 | 16 | 13 | 16
| 912 | 3 | 9 | 7 | 2 | 8 | 13 | 14 | 11 | 19 | 15 | 19
| 913 | 7 | 11 | 11 | 3 | 7 | 17 | 10 | 9 | 14 | 15 | 17
| 914 | 0 | 7 | 9 | 2 | 6 | 10 | 10 | 8 | 12 | 13 | 13
| 915 | 4 | 8 | 8 | 2 | 6 | 14 | 9 | 8 | 16 | 15 | 16
| 916 | 7 | 8 | 10 | 2 | 5 | 17 | 11 | 11 | 15 | 11 | 17
| 917 | 4 | 6 | 9 | 1 | 7 | 8 | 10 | 8 | 13 | 14 | 14
| 918 | 5 | 9 | 8 | 3 | 7 | 15 | 12 | 7 | 13 | 13 | 15
| 919 | 3 | 8 | 9 | 3 | 9 | 14 | 16 | 12 | 17 | 23 | 23
| 920 | 2 | 10 | 9 | 1 | 6 | 14 | 10 | 7 | 12 | 15 | 15
| 921 | 1 | 8 | 9 | 3 | 8 | 16 | 11 | 8 | 13 | 14 | 16
| 922 | 7 | 10 | 10 | 3 | 5 | 14 | 6 | 8 | 14 | 14 | 14
| 923 | 6 | 9 | 9 | 2 | 4 | 11 | 9 | 8 | 12 | 16 | 16
| 924 | 3 | 11 | 9 | 2 | 7 | 14 | 9 | 11 | 15 | 14 | 15
| 925 | 5 | 8 | 8 | 2 | 5 | 15 | 10 | 8 | 15 | 14 | 15
| 926 | 4 | 8 | 7 | 3 | 8 | 16 | 10 | 9 | 17 | 16 | 17
| 927 | 3 | 9 | 7 | 2 | 6 | 14 | 12 | 10 | 17 | 16 | 17
| 928 | 8 | 13 | 11 | 2 | 7 | 17 | 9 | 7 | 16 | 15 | 17
| 929 | 6 | 8 | 10 | 2 | 7 | 11 | 12 | 9 | 13 | 14 | 14
| 930 | 5 | 10 | 10 | 3 | 6 | 12 | 8 | 9 | 11 | 14 | 14
| 931 | 4 | 8 | 6 | 2 | 9 | 15 | 9 | 12 | 14 | 17 | 17
| 932 | 5 | 8 | 10 | 2 | 6 | 12 | 10 | 7 | 14 | 17 | 17
| 933 | 1 | 7 | 5 | 2 | 3 | 14 | 11 | 5 | 14 | 14 | 14
| 934 | 2 | 6 | 7 | 3 | 6 | 9 | 13 | 12 | 14 | 17 | 17
| 935 | 5 | 9 | 8 | 1 | 7 | 12 | 8 | 9 | 14 | 14 | 14
| 936 | 5 | 8 | 7 | 3 | 4 | 14 | 12 | 8 | 15 | 17 | 17
| 937 | 5 | 8 | 8 | 3 | 5 | 14 | 8 | 11 | 11 | 17 | 17
| 938 | 6 | 8 | 10 | 3 | 6 | 12 | 6 | 13 | 14 | 15 | 15
| 939 | 3 | 5 | 9 | 3 | 6 | 16 | 11 | 11 | 14 | 13 | 16
| 940 | 5 | 6 | 11 | 3 | 6 | 10 | 12 | 10 | 14 | 17 | 17
| 941 | 5 | 10 | 9 | 3 | 8 | 12 | 11 | 12 | 15 | 11 | 15
| 942 | 3 | 7 | 7 | 4 | 7 | 12 | 7 | 10 | 10 | 12 | 12
| 943 | 5 | 8 | 9 | 2 | 5 | 14 | 10 | 6 | 12 | 16 | 16
| 944 | 5 | 7 | 7 | 2 | 4 | 12 | 7 | 8 | 18 | 10 | 18
| 945 | 5 | 7 | 6 | 2 | 4 | 13 | 13 | 8 | 17 | 12 | 17
| 946 | 5 | 5 | 7 | 3 | 6 | 13 | 12 | 9 | 14 | 17 | 17
| 947 | 4 | 9 | 9 | 3 | 4 | 14 | 6 | 5 | 15 | 12 | 15
| 948 | 8 | 11 | 10 | 4 | 5 | 8 | 9 | 9 | 14 | 13 | 14
| 949 | 3 | 11 | 7 | 2 | 4 | 14 | 11 | 6 | 13 | 15 | 15
| 950 | 3 | 8 | 8 | 3 | 9 | 17 | 14 | 13 | 20 | 16 | 20
| 951 | 8 | 13 | 11 | 2 | 8 | 12 | 12 | 9 | 15 | 17 | 17
| 952 | 4 | 9 | 11 | 3 | 7 | 17 | 11 | 11 | 12 | 16 | 17
| 953 | 7 | 8 | 9 | 1 | 7 | 10 | 11 | 6 | 14 | 17 | 17
| 954 | 1 | 9 | 6 | 3 | 6 | 13 | 11 | 9 | 14 | 14 | 14
| 955 | 8 | 12 | 12 | 2 | 6 | 13 | 11 | 12 | 15 | 12 | 15
| 956 | 3 | 10 | 9 | 2 | 9 | 15 | 11 | 12 | 16 | 12 | 16
| 957 | 1 | 9 | 8 | 2 | 3 | 10 | 8 | 9 | 15 | 15 | 15
| 958 | 5 | 8 | 8 | 3 | 6 | 9 | 13 | 9 | 16 | 14 | 16
| 959 | 5 | 9 | 8 | 2 | 7 | 11 | 13 | 11 | 18 | 18 | 18
| 960 | 5 | 11 | 8 | 2 | 8 | 10 | 8 | 14 | 13 | 16 | 16
| 961 | 5 | 8 | 9 | 4 | 6 | 9 | 9 | 9 | 11 | 13 | 13
| 962 | 6 | 7 | 9 | 4 | 6 | 12 | 11 | 12 | 16 | 16 | 16
| 963 | 6 | 13 | 9 | 1 | 7 | 15 | 8 | 7 | 13 | 14 | 15
| 964 | 5 | 12 | 10 | 2 | 6 | 13 | 12 | 9 | 17 | 12 | 17
| 965 | 6 | 8 | 7 | 3 | 9 | 17 | 13 | 16 | 16 | 18 | 18
| 966 | 6 | 10 | 10 | 3 | 7 | 12 | 12 | 11 | 17 | 15 | 17
| 967 | 5 | 6 | 10 | 1 | 5 | 11 | 7 | 6 | 13 | 13 | 13
| 968 | 6 | 10 | 11 | 4 | 5 | 11 | 10 | 10 | 15 | 13 | 15
| 969 | 4 | 7 | 8 | 2 | 6 | 14 | 12 | 10 | 14 | 16 | 16
| 970 | 4 | 10 | 11 | 2 | 5 | 10 | 9 | 10 | 16 | 14 | 16
| 971 | 6 | 8 | 10 | 3 | 7 | 7 | 14 | 11 | 17 | 16 | 17
| 972 | 6 | 10 | 10 | 2 | 5 | 10 | 13 | 11 | 14 | 16 | 16
| 973 | 2 | 5 | 6 | 2 | 6 | 13 | 7 | 12 | 12 | 16 | 16
| 974 | 1 | 8 | 8 | 2 | 6 | 10 | 13 | 8 | 16 | 18 | 18
| 975 | 4 | 10 | 11 | 3 | 6 | 8 | 8 | 9 | 13 | 13 | 13
| 976 | 2 | 8 | 10 | 3 | 3 | 11 | 11 | 9 | 16 | 13 | 16
| 977 | 2 | 8 | 9 | 2 | 7 | 15 | 10 | 9 | 16 | 15 | 16
| 978 | 2 | 9 | 8 | 1 | 8 | 14 | 10 | 8 | 12 | 15 | 15
| 979 | 5 | 6 | 10 | 4 | 7 | 14 | 9 | 11 | 14 | 12 | 14
| 980 | 3 | 11 | 10 | 2 | 5 | 16 | 11 | 9 | 14 | 14 | 16
| 981 | 8 | 8 | 11 | 1 | 7 | 14 | 10 | 11 | 16 | 17 | 17
| 982 | 4 | 8 | 9 | 2 | 6 | 11 | 6 | 7 | 16 | 17 | 17
| 983 | 7 | 12 | 7 | 2 | 7 | 10 | 9 | 10 | 13 | 13 | 13
| 984 | 5 | 8 | 5 | 3 | 5 | 12 | 7 | 8 | 14 | 11 | 14
| 985 | 5 | 10 | 10 | 2 | 5 | 15 | 8 | 9 | 14 | 13 | 15
| 986 | 7 | 11 | 8 | 3 | 6 | 15 | 12 | 9 | 14 | 13 | 15
| 987 | 6 | 10 | 11 | 3 | 9 | 15 | 10 | 12 | 15 | 14 | 15
| 988 | 4 | 9 | 9 | 1 | 5 | 14 | 9 | 10 | 15 | 14 | 15
| 989 | 5 | 10 | 12 | 3 | 3 | 8 | 14 | 7 | 16 | 15 | 16
| 990 | 4 | 8 | 7 | 4 | 6 | 11 | 10 | 8 | 15 | 15 | 15
| 991 | 3 | 9 | 10 | 2 | 7 | 16 | 10 | 12 | 14 | 15 | 16
| 992 | 4 | 10 | 10 | 2 | 6 | 7 | 11 | 12 | 17 | 13 | 17
| 993 | 6 | 6 | 9 | 3 | 7 | 14 | 8 | 12 | 18 | 16 | 18
| 994 | 3 | 9 | 10 | 2 | 5 | 7 | 12 | 6 | 16 | 14 | 16
| 995 | 2 | 10 | 9 | 1 | 7 | 10 | 13 | 9 | 18 | 16 | 18
| 996 | 5 | 10 | 9 | 2 | 6 | 15 | 11 | 12 | 15 | 17 | 17
| 997 | 5 | 8 | 7 | 4 | 8 | 14 | 12 | 13 | 18 | 12 | 18
| 998 | 5 | 6 | 9 | 4 | 4 | 13 | 6 | 7 | 14 | 10 | 14
| 999 | 8 | 9 | 10 | 2 | 4 | 14 | 13 | 8 | 18 | 16 | 18
| 1000 | 4 | 8 | 7 | 3 | 7 | 9 | 10 | 11 | 17 | 14 | 17

## SIPmath Chart Data (hidden)
| Finish01 | Finish02 | Finish03 | Finish04 | Finish05 | Finish06 | Finish07 | Finish08 | Finish09 | Finish10 | Finish -
Expected Value | 4 | 9 | 9 | 2 | 6 | 13 | 10 | 9 | 15 | 15 | 16
Series Name | Finish01 EV 4 | Finish02 EV 9 | Finish03 EV 9 | Finish04 EV 2 | Finish05 EV 6 | Finish06 EV 13 | Finish07 EV 10 | Finish08 EV 9 | Finish09 EV 15 | Finish10 EV 15 | Finish - Average=16
Integer chart? | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
Loss Exceedance | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Number of Bins | 9 | 11 | 10 | 4 | 8 | 13 | 11 | 14 | 13 | 14 | 13
Label position | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Bin Width | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Decimals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scale | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Use Axis Title? | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Axis Title
Min | -1 | 3 | 4 | 0 | 2 | 6 | 5 | 2 | 9 | 9 | 11
Bin Range | 0 | 4 | 5 | 1 | 3 | 7 | 6 | 3 | 10 | 10 | 12
Frequency | 1 | 5 | 6 | 2 | 4 | 8 | 7 | 4 | 11 | 11 | 13
Labels | 2 | 6 | 7 | 3 | 5 | 9 | 8 | 5 | 12 | 12 | 14
Cumulative | 3 | 7 | 8 | 4 | 6 | 10 | 9 | 6 | 13 | 13 | 15
| 4 | 8 | 9 | 5 | 7 | 11 | 10 | 7 | 14 | 14 | 16
| 5 | 9 | 10 | 6 | 8 | 12 | 11 | 8 | 15 | 15 | 17
| 6 | 10 | 11 | 7 | 9 | 13 | 12 | 9 | 16 | 16 | 18
| 7 | 11 | 12 | 8 | 10 | 14 | 13 | 10 | 17 | 17 | 19
| 8 | 12 | 13 | 9 | 11 | 15 | 14 | 11 | 18 | 18 | 20
| 9 | 13 | 14 | 10 | 12 | 16 | 15 | 12 | 19 | 19 | 21
| 10 | 14 | 15 | 11 | 13 | 17 | 16 | 13 | 20 | 20 | 22
| 11 | 15 | 16 | 12 | 14 | 18 | 17 | 14 | 21 | 21 | 23
| 12 | 16 | 17 | 13 | 15 | 19 | 18 | 15 | 22 | 22 | 24
| 13 | 17 | 18 | 14 | 16 | 20 | 19 | 16 | 23 | 23 | 25
| 14 | 18 | 19 | 15 | 17 | 21 | 20 | 17 | 24 | 24 | 26
| 15 | 19 | 20 | 16 | 18 | 22 | 21 | 18 | 25 | 25 | 27
| 16 | 20 | 21 | 17 | 19 | 23 | 22 | 19 | 26 | 26 | 28
| 17 | 21 | 22 | 18 | 20 | 24 | 23 | 20 | 27 | 27 | 29
| 18 | 22 | 23 | 19 | 21 | 25 | 24 | 21 | 28 | 28 | 30
| 19 | 23 | 24 | 20 | 22 | 26 | 25 | 22 | 29 | 29 | 31
| 20 | 24 | 25 | 21 | 23 | 27 | 26 | 23 | 30 | 30 | 32
| 21 | 25 | 26 | 22 | 24 | 28 | 27 | 24 | 31 | 31 | 33
| 22 | 26 | 27 | 23 | 25 | 29 | 28 | 25 | 32 | 32 | 34
| 23 | 27 | 28 | 24 | 26 | 30 | 29 | 26 | 33 | 33 | 35
| 24 | 28 | 29 | 25 | 27 | 31 | 30 | 27 | 34 | 34 | 36
| 25 | 29 | 30 | 26 | 28 | 32 | 31 | 28 | 35 | 35 | 37
| 26 | 30 | 31 | 27 | 29 | 33 | 32 | 29 | 36 | 36 | 38
| 27 | 31 | 32 | 28 | 30 | 34 | 33 | 30 | 37 | 37 | 39
| 28 | 32 | 33 | 29 | 31 | 35 | 34 | 31 | 38 | 38 | 40
| 29 | 33 | 34 | 30 | 32 | 36 | 35 | 32 | 39 | 39 | 41
| 30 | 34 | 35 | 31 | 33 | 37 | 36 | 33 | 40 | 40 | 42
| 31 | 35 | 36 | 32 | 34 | 38 | 37 | 34 | 41 | 41 | 43
| 32 | 36 | 37 | 33 | 35 | 39 | 38 | 35 | 42 | 42 | 44
| 33 | 37 | 38 | 34 | 36 | 40 | 39 | 36 | 43 | 43 | 45
| 34 | 38 | 39 | 35 | 37 | 41 | 40 | 37 | 44 | 44 | 46
| 35 | 39 | 40 | 36 | 38 | 42 | 41 | 38 | 45 | 45 | 47
| 36 | 40 | 41 | 37 | 39 | 43 | 42 | 39 | 46 | 46 | 48
| 37 | 41 | 42 | 38 | 40 | 44 | 43 | 40 | 47 | 47 | 49
| 38 | 42 | 43 | 39 | 41 | 45 | 44 | 41 | 48 | 48 | 50
| 39 | 43 | 44 | 40 | 42 | 46 | 45 | 42 | 49 | 49 | 51
| 40 | 44 | 45 | 41 | 43 | 47 | 46 | 43 | 50 | 50 | 52
| 41 | 45 | 46 | 42 | 44 | 48 | 47 | 44 | 51 | 51 | 53
| 42 | 46 | 47 | 43 | 45 | 49 | 48 | 45 | 52 | 52 | 54
| 43 | 47 | 48 | 44 | 46 | 50 | 49 | 46 | 53 | 53 | 55
| 44 | 48 | 49 | 45 | 47 | 51 | 50 | 47 | 54 | 54 | 56
| 45 | 49 | 50 | 46 | 48 | 52 | 51 | 48 | 55 | 55 | 57
| 46 | 50 | 51 | 47 | 49 | 53 | 52 | 49 | 56 | 56 | 58
| 47 | 51 | 52 | 48 | 50 | 54 | 53 | 50 | 57 | 57 | 59
| 48 | 52 | 53 | 49 | 51 | 55 | 54 | 51 | 58 | 58 | 60
| 49 | 53 | 54 | 50 | 52 | 56 | 55 | 52 | 59 | 59 | 61
| 50 | 54 | 55 | 51 | 53 | 57 | 56 | 53 | 60 | 60 | 62
| 51 | 55 | 56 | 52 | 54 | 58 | 57 | 54 | 61 | 61 | 63
| 52 | 56 | 57 | 53 | 55 | 59 | 58 | 55 | 62 | 62 | 64
| 53 | 57 | 58 | 54 | 56 | 60 | 59 | 56 | 63 | 63 | 65
| 54 | 58 | 59 | 55 | 57 | 61 | 60 | 57 | 64 | 64 | 66
| 55 | 59 | 60 | 56 | 58 | 62 | 61 | 58 | 65 | 65 | 67
| 56 | 60 | 61 | 57 | 59 | 63 | 62 | 59 | 66 | 66 | 68
| 57 | 61 | 62 | 58 | 60 | 64 | 63 | 60 | 67 | 67 | 69
| 58 | 62 | 63 | 59 | 61 | 65 | 64 | 61 | 68 | 68 | 70
| 59 | 63 | 64 | 60 | 62 | 66 | 65 | 62 | 69 | 69 | 71
| 60 | 64 | 65 | 61 | 63 | 67 | 66 | 63 | 70 | 70 | 72
| 61 | 65 | 66 | 62 | 64 | 68 | 67 | 64 | 71 | 71 | 73
| 62 | 66 | 67 | 63 | 65 | 69 | 68 | 65 | 72 | 72 | 74
| 63 | 67 | 68 | 64 | 66 | 70 | 69 | 66 | 73 | 73 | 75
| 64 | 68 | 69 | 65 | 67 | 71 | 70 | 67 | 74 | 74 | 76
| 65 | 69 | 70 | 66 | 68 | 72 | 71 | 68 | 75 | 75 | 77
| 66 | 70 | 71 | 67 | 69 | 73 | 72 | 69 | 76 | 76 | 78
| 67 | 71 | 72 | 68 | 70 | 74 | 73 | 70 | 77 | 77 | 79
| 68 | 72 | 73 | 69 | 71 | 75 | 74 | 71 | 78 | 78 | 80
| 69 | 73 | 74 | 70 | 72 | 76 | 75 | 72 | 79 | 79 | 81
| 70 | 74 | 75 | 71 | 73 | 77 | 76 | 73 | 80 | 80 | 82
| 71 | 75 | 76 | 72 | 74 | 78 | 77 | 74 | 81 | 81 | 83
| 72 | 76 | 77 | 73 | 75 | 79 | 78 | 75 | 82 | 82 | 84
| 73 | 77 | 78 | 74 | 76 | 80 | 79 | 76 | 83 | 83 | 85
| 74 | 78 | 79 | 75 | 77 | 81 | 80 | 77 | 84 | 84 | 86
| 75 | 79 | 80 | 76 | 78 | 82 | 81 | 78 | 85 | 85 | 87
| 76 | 80 | 81 | 77 | 79 | 83 | 82 | 79 | 86 | 86 | 88
| 77 | 81 | 82 | 78 | 80 | 84 | 83 | 80 | 87 | 87 | 89
| 78 | 82 | 83 | 79 | 81 | 85 | 84 | 81 | 88 | 88 | 90
| 79 | 83 | 84 | 80 | 82 | 86 | 85 | 82 | 89 | 89 | 91
| 80 | 84 | 85 | 81 | 83 | 87 | 86 | 83 | 90 | 90 | 92
| 81 | 85 | 86 | 82 | 84 | 88 | 87 | 84 | 91 | 91 | 93
| 82 | 86 | 87 | 83 | 85 | 89 | 88 | 85 | 92 | 92 | 94
| 83 | 87 | 88 | 84 | 86 | 90 | 89 | 86 | 93 | 93 | 95
| 84 | 88 | 89 | 85 | 87 | 91 | 90 | 87 | 94 | 94 | 96
| 85 | 89 | 90 | 86 | 88 | 92 | 91 | 88 | 95 | 95 | 97
| 86 | 90 | 91 | 87 | 89 | 93 | 92 | 89 | 96 | 96 | 98
| 87 | 91 | 92 | 88 | 90 | 94 | 93 | 90 | 97 | 97 | 99
| 88 | 92 | 93 | 89 | 91 | 95 | 94 | 91 | 98 | 98 | 100
| 89 | 93 | 94 | 90 | 92 | 96 | 95 | 92 | 99 | 99 | 101
| 90 | 94 | 95 | 91 | 93 | 97 | 96 | 93 | 100 | 100 | 102
| 91 | 95 | 96 | 92 | 94 | 98 | 97 | 94 | 101 | 101 | 103
| 92 | 96 | 97 | 93 | 95 | 99 | 98 | 95 | 102 | 102 | 104
| 93 | 97 | 98 | 94 | 96 | 100 | 99 | 96 | 103 | 103 | 105
| 94 | 98 | 99 | 95 | 97 | 101 | 100 | 97 | 104 | 104 | 106
| 95 | 99 | 100 | 96 | 98 | 102 | 101 | 98 | 105 | 105 | 107
| 96 | 100 | 101 | 97 | 99 | 103 | 102 | 99 | 106 | 106 | 108
| 97 | 101 | 102 | 98 | 100 | 104 | 103 | 100 | 107 | 107 | 109
| 98 | 102 | 103 | 99 | 101 | 105 | 104 | 101 | 108 | 108 | 110
| 99 | 103 | 104 | 100 | 102 | 106 | 105 | 102 | 109 | 109 | 111
| 100 | 104 | 105 | 101 | 103 | 107 | 106 | 103 | 110 | 110 | 112
| 101 | 105 | 106 | 102 | 104 | 108 | 107 | 104 | 111 | 111 | 113
| 0.024 | 0.013 | 0.023 | 0.13 | 0.039 | 0.012 | 0.021 | 0.004 | 0.012 | 0.017 | 0.014 | 0.014
| 0.054 | 0.068 | 0.097 | 0.392 | 0.114 | 0.03 | 0.06 | 0.01 | 0.061 | 0.05 | 0.04 | 0.04
| 0.104 | 0.086 | 0.161 | 0.355 | 0.178 | 0.052 | 0.093 | 0.047 | 0.09 | 0.089 | 0.101 | 0.101
| 0.148 | 0.124 | 0.193 | 0.123 | 0.218 | 0.078 | 0.137 | 0.059 | 0.129 | 0.136 | 0.219 | 0.219
| 0.199 | 0.19 | 0.227 | 0 | 0.224 | 0.089 | 0.159 | 0.115 | 0.185 | 0.163 | 0.247 | 0.247
| 0.209 | 0.191 | 0.149 | 0 | 0.153 | 0.114 | 0.217 | 0.116 | 0.155 | 0.181 | 0.204 | 0.204
| 0.147 | 0.168 | 0.097 | 0 | 0.069 | 0.149 | 0.16 | 0.162 | 0.163 | 0.163 | 0.122 | 0.122
| 0.083 | 0.091 | 0.047 | 0 | 0.005 | 0.149 | 0.098 | 0.142 | 0.104 | 0.113 | 0.033 | 0.033
| 0.032 | 0.051 | 0.005 | 0 | 0 | 0.169 | 0.041 | 0.139 | 0.071 | 0.057 | 0.012 | 0.012
| 0 | 0.016 | 0.001 | 0 | 0 | 0.094 | 0.012 | 0.091 | 0.02 | 0.018 | 0.005 | 0.005
| 0 | 0.002 | 0 | 0 | 0 | 0.052 | 0.002 | 0.067 | 0.008 | 0.007 | 0.002 | 0.002
| 0 | 0 | 0 | 0 | 0 | 0.011 | 0 | 0.036 | 0.001 | 0.004 | 0.001 | 0.001
| 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0.009 | 0.001 | 0.001 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003 | 0 | 0.001 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 4 | 5 | 1 | 3 | 7 | 6 | 3 | 10 | 10 | 11
| 1 | 5 | 6 | 2 | 4 | 8 | 7 | 4 | 11 | 11 | 12
| 2 | 6 | 7 | 3 | 5 | 9 | 8 | 5 | 12 | 12 | 13
| 3 | 7 | 8 | 4 | 6 | 10 | 9 | 6 | 13 | 13 | 14
| 4 | 8 | 9 | 5 | 7 | 11 | 10 | 7 | 14 | 14 | 15
| 5 | 9 | 10 | 6 | 8 | 12 | 11 | 8 | 15 | 15 | 16
| 6 | 10 | 11 | 7 | 9 | 13 | 12 | 9 | 16 | 16 | 17
| 7 | 11 | 12 | 8 | 10 | 14 | 13 | 10 | 17 | 17 | 18
| 8 | 12 | 13 | 9 | 11 | 15 | 14 | 11 | 18 | 18 | 19
| 9 | 13 | 14 | 10 | 12 | 16 | 15 | 12 | 19 | 19 | 20
| 10 | 14 | 15 | 11 | 13 | 17 | 16 | 13 | 20 | 20 | 21
| 11 | 15 | 16 | 12 | 14 | 18 | 17 | 14 | 21 | 21 | 22
| 12 | 16 | 17 | 13 | 15 | 19 | 18 | 15 | 22 | 22 | 23
| 13 | 17 | 18 | 14 | 16 | 20 | 19 | 16 | 23 | 23 | 24
| 14 | 18 | 19 | 15 | 17 | 21 | 20 | 17 | 24 | 24 | 25
| 15 | 19 | 20 | 16 | 18 | 22 | 21 | 18 | 25 | 25 | 26
| 16 | 20 | 21 | 17 | 19 | 23 | 22 | 19 | 26 | 26 | 27
| 17 | 21 | 22 | 18 | 20 | 24 | 23 | 20 | 27 | 27 | 28
| 18 | 22 | 23 | 19 | 21 | 25 | 24 | 21 | 28 | 28 | 29
| 19 | 23 | 24 | 20 | 22 | 26 | 25 | 22 | 29 | 29 | 30
| 20 | 24 | 25 | 21 | 23 | 27 | 26 | 23 | 30 | 30 | 31
| 21 | 25 | 26 | 22 | 24 | 28 | 27 | 24 | 31 | 31 | 32
| 22 | 26 | 27 | 23 | 25 | 29 | 28 | 25 | 32 | 32 | 33
| 23 | 27 | 28 | 24 | 26 | 30 | 29 | 26 | 33 | 33 | 34
| 24 | 28 | 29 | 25 | 27 | 31 | 30 | 27 | 34 | 34 | 35
| 25 | 29 | 30 | 26 | 28 | 32 | 31 | 28 | 35 | 35 | 36
| 26 | 30 | 31 | 27 | 29 | 33 | 32 | 29 | 36 | 36 | 37
| 27 | 31 | 32 | 28 | 30 | 34 | 33 | 30 | 37 | 37 | 38
| 28 | 32 | 33 | 29 | 31 | 35 | 34 | 31 | 38 | 38 | 39
| 29 | 33 | 34 | 30 | 32 | 36 | 35 | 32 | 39 | 39 | 40
| 30 | 34 | 35 | 31 | 33 | 37 | 36 | 33 | 40 | 40 | 41
| 31 | 35 | 36 | 32 | 34 | 38 | 37 | 34 | 41 | 41 | 42
| 32 | 36 | 37 | 33 | 35 | 39 | 38 | 35 | 42 | 42 | 43
| 33 | 37 | 38 | 34 | 36 | 40 | 39 | 36 | 43 | 43 | 44
| 34 | 38 | 39 | 35 | 37 | 41 | 40 | 37 | 44 | 44 | 45
| 35 | 39 | 40 | 36 | 38 | 42 | 41 | 38 | 45 | 45 | 46
| 36 | 40 | 41 | 37 | 39 | 43 | 42 | 39 | 46 | 46 | 47
| 37 | 41 | 42 | 38 | 40 | 44 | 43 | 40 | 47 | 47 | 48
| 38 | 42 | 43 | 39 | 41 | 45 | 44 | 41 | 48 | 48 | 49
| 39 | 43 | 44 | 40 | 42 | 46 | 45 | 42 | 49 | 49 | 50
| 40 | 44 | 45 | 41 | 43 | 47 | 46 | 43 | 50 | 50 | 51
| 41 | 45 | 46 | 42 | 44 | 48 | 47 | 44 | 51 | 51 | 52
| 42 | 46 | 47 | 43 | 45 | 49 | 48 | 45 | 52 | 52 | 53
| 43 | 47 | 48 | 44 | 46 | 50 | 49 | 46 | 53 | 53 | 54
| 44 | 48 | 49 | 45 | 47 | 51 | 50 | 47 | 54 | 54 | 55
| 45 | 49 | 50 | 46 | 48 | 52 | 51 | 48 | 55 | 55 | 56
| 46 | 50 | 51 | 47 | 49 | 53 | 52 | 49 | 56 | 56 | 57
| 47 | 51 | 52 | 48 | 50 | 54 | 53 | 50 | 57 | 57 | 58
| 48 | 52 | 53 | 49 | 51 | 55 | 54 | 51 | 58 | 58 | 59
| 49 | 53 | 54 | 50 | 52 | 56 | 55 | 52 | 59 | 59 | 60
| 50 | 54 | 55 | 51 | 53 | 57 | 56 | 53 | 60 | 60 | 61
| 51 | 55 | 56 | 52 | 54 | 58 | 57 | 54 | 61 | 61 | 62
| 52 | 56 | 57 | 53 | 55 | 59 | 58 | 55 | 62 | 62 | 63
| 53 | 57 | 58 | 54 | 56 | 60 | 59 | 56 | 63 | 63 | 64
| 54 | 58 | 59 | 55 | 57 | 61 | 60 | 57 | 64 | 64 | 65
| 55 | 59 | 60 | 56 | 58 | 62 | 61 | 58 | 65 | 65 | 66
| 56 | 60 | 61 | 57 | 59 | 63 | 62 | 59 | 66 | 66 | 67
| 57 | 61 | 62 | 58 | 60 | 64 | 63 | 60 | 67 | 67 | 68
| 58 | 62 | 63 | 59 | 61 | 65 | 64 | 61 | 68 | 68 | 69
| 59 | 63 | 64 | 60 | 62 | 66 | 65 | 62 | 69 | 69 | 70
| 60 | 64 | 65 | 61 | 63 | 67 | 66 | 63 | 70 | 70 | 71
| 61 | 65 | 66 | 62 | 64 | 68 | 67 | 64 | 71 | 71 | 72
| 62 | 66 | 67 | 63 | 65 | 69 | 68 | 65 | 72 | 72 | 73
| 63 | 67 | 68 | 64 | 66 | 70 | 69 | 66 | 73 | 73 | 74
| 64 | 68 | 69 | 65 | 67 | 71 | 70 | 67 | 74 | 74 | 75
| 65 | 69 | 70 | 66 | 68 | 72 | 71 | 68 | 75 | 75 | 76
| 66 | 70 | 71 | 67 | 69 | 73 | 72 | 69 | 76 | 76 | 77
| 67 | 71 | 72 | 68 | 70 | 74 | 73 | 70 | 77 | 77 | 78
| 68 | 72 | 73 | 69 | 71 | 75 | 74 | 71 | 78 | 78 | 79
| 69 | 73 | 74 | 70 | 72 | 76 | 75 | 72 | 79 | 79 | 80
| 70 | 74 | 75 | 71 | 73 | 77 | 76 | 73 | 80 | 80 | 81
| 71 | 75 | 76 | 72 | 74 | 78 | 77 | 74 | 81 | 81 | 82
| 72 | 76 | 77 | 73 | 75 | 79 | 78 | 75 | 82 | 82 | 83
| 73 | 77 | 78 | 74 | 76 | 80 | 79 | 76 | 83 | 83 | 84
| 74 | 78 | 79 | 75 | 77 | 81 | 80 | 77 | 84 | 84 | 85
| 75 | 79 | 80 | 76 | 78 | 82 | 81 | 78 | 85 | 85 | 86
| 76 | 80 | 81 | 77 | 79 | 83 | 82 | 79 | 86 | 86 | 87
| 77 | 81 | 82 | 78 | 80 | 84 | 83 | 80 | 87 | 87 | 88
| 78 | 82 | 83 | 79 | 81 | 85 | 84 | 81 | 88 | 88 | 89
| 79 | 83 | 84 | 80 | 82 | 86 | 85 | 82 | 89 | 89 | 90
| 80 | 84 | 85 | 81 | 83 | 87 | 86 | 83 | 90 | 90 | 91
| 81 | 85 | 86 | 82 | 84 | 88 | 87 | 84 | 91 | 91 | 92
| 82 | 86 | 87 | 83 | 85 | 89 | 88 | 85 | 92 | 92 | 93
| 83 | 87 | 88 | 84 | 86 | 90 | 89 | 86 | 93 | 93 | 94
| 84 | 88 | 89 | 85 | 87 | 91 | 90 | 87 | 94 | 94 | 95
| 85 | 89 | 90 | 86 | 88 | 92 | 91 | 88 | 95 | 95 | 96
| 86 | 90 | 91 | 87 | 89 | 93 | 92 | 89 | 96 | 96 | 97
| 87 | 91 | 92 | 88 | 90 | 94 | 93 | 90 | 97 | 97 | 98
| 88 | 92 | 93 | 89 | 91 | 95 | 94 | 91 | 98 | 98 | 99
| 89 | 93 | 94 | 90 | 92 | 96 | 95 | 92 | 99 | 99 | 100
| 90 | 94 | 95 | 91 | 93 | 97 | 96 | 93 | 100 | 100 | 101
| 91 | 95 | 96 | 92 | 94 | 98 | 97 | 94 | 101 | 101 | 102
| 92 | 96 | 97 | 93 | 95 | 99 | 98 | 95 | 102 | 102 | 103
| 93 | 97 | 98 | 94 | 96 | 100 | 99 | 96 | 103 | 103 | 104
| 94 | 98 | 99 | 95 | 97 | 101 | 100 | 97 | 104 | 104 | 105
| 95 | 99 | 100 | 96 | 98 | 102 | 101 | 98 | 105 | 105 | 106
| 96 | 100 | 101 | 97 | 99 | 103 | 102 | 99 | 106 | 106 | 107
| 97 | 101 | 102 | 98 | 100 | 104 | 103 | 100 | 107 | 107 | 108
| 98 | 102 | 103 | 99 | 101 | 105 | 104 | 101 | 108 | 108 | 109
| 99 | 103 | 104 | 100 | 102 | 106 | 105 | 102 | 109 | 109 | 110
| 100 | 104 | 105 | 101 | 103 | 107 | 106 | 103 | 110 | 110 | 111
| 101 | 105 | 106 | 102 | 104 | 108 | 107 | 104 | 111 | 111 | 112
0.001
0.004
0.007
0.01
0.02
0.03
0.04
0.05
0.06
0.07
0.08
0.09
0.1
0.11
0.12
0.13
0.14
0.15
0.16
0.17
0.18
0.19
0.2
0.21
0.22
0.23
0.24
0.25
0.26
0.27
0.28
0.29
0.3
0.31
0.32
0.33
0.34
0.35
0.36
0.37
0.38
0.39
0.4
0.41
0.42
0.43
0.44
0.45
0.46
0.47
0.48
0.49
0.5
0.51
0.52
0.53
0.54
0.55
0.56
0.57
0.58
0.59
0.6
0.61
0.62
0.63
0.64
0.65
0.66
0.67
0.68
0.69
0.7
0.71
0.72
0.73
0.74
0.75
0.76
0.77
0.78
0.79
0.8
0.81
0.82
0.83
0.84
0.85
0.86
0.87
0.88
0.89
0.9
0.91
0.92
0.93
0.94
0.95
0.96
0.97
0.98
0.99
0.993
0.996
0.999